Ecuador

| Programme Title: | Youth, Employment, Migration – Reducing Inequalities in Ecuador |
| --- | --- |
| Programme number & MDTF ref: | MDGF-1936-H-ECU Youth Employme (67212) |
| Window: | Youth, Employment & Migration |
| Approved Budget by NSC (US$): | 5.7 million |
| Participating Organizations: | UNFPA, UNDP, IOM, ILO, UNICEF |
| First Tranche transferred on: | 28-May-2009 |

ACTIVITIES Reported:

Main Substantive Activities:

500 youth took part in activities designed to incorporate them into the labor market. 18 financial institutions involved in entrepreneurial development training plan. Procedures manual developed on dealing with children and adolescents in situations of migration. Pilot plan to decentralize migration competencies to 5 municipalities developed.

Problems and lessons learned:

External to JP: staff rotation amongst stakeholders, political differences between national and local governments, insufficient participation of Ministry of Labour.

The programme reports relevant linkage to the UNDAF: Yes

The programme has communications strategy in place: No

CHARTS & FIGURES

As of 31 December 2010