Egypt

| Programme Title: | Mobilization of the Dahshur World Heritage Site for Community Development |
| --- | --- |
| Programme number & MDTF ref: | MDGF-1775-G-EGY Dahshur World (67175) |
| Window: | Culture & Development |
| Approved Budget by NSC (US$): | 3.09 million |
| Participating Organizations: | UNDP, UNESCO, UNIDO, UNWTO, ILO |
| First Tranche transferred on: | 13-Apr-2009 |
| Second Tranche transferred on: | 23-Aug-2010 |

ACTIVITIES Reported:

Main Substantive Activities:

Baseline studies completed. 1500 persons trained in community capacity building techniques. Business development and micro-finance services introduced. 40 people (20 women) getting financing and 60 vocational training. Strategic plans developed for environment, culture and tourism. Training in ready-made garments underway. Multiple workshops carried out.

Problems and lessons learned:

Managerial (difficulty coordinating many actors). UN Agency coordination (multiple regulations). Egyptian Revolution has put the project on hold for + 3 months. Interim Govt and changes of national partners impacted the pace of delivery.

The programme reports relevant linkage to the UNDAF: Yes

The programme has communications strategy in place: Yes (now the JP is implementing the action plan of the strategy)

CHARTS & FIGURES

As of 31 December 2010