Annexe 5 M& E Framework

MDG-F China Culture and Development Partnership Framework

| Expected Results | Indicators | Means of verification | Collection methods | Responsibilities |  | Baseline value of indicators | Value of indicators (as of 31 Dec 2011) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MDG Goals & indicators relevant to the programme: Goal 1: Eradicate Extreme Poverty Indicator 1. Proportion of population below $1 (PPP) per day Indicator 2. Poverty gap ratio [incidence x depth of poverty] Indicator 3. Share of poorest quintile in national consumption Indicator 4. Prevalence of underweight children under-five years of age Goal 2: Universal Primary Education Indicator 6. Net enrolment ratio in primary education Indicator 7. Proportion of pupils starting grade 1 who reach grade 5 Indicator 8. Literacy rate of 15-24 year-olds Goal 3: Gender Equality Indicator 9. Ratios of girls to boys in primary, secondary and tertiary education Indicator 10. Ratio of literate women to men, 15-24 years old Indicator 11. Share of women in wage employment in the non-agricultural sector Goal 4: Reduce Child Mortality Indicator 13. Under-five mortality rate Indicator 14. Infant mortality rate Indicator 15. Proportion of 1 year-old children immunised against measles Goal 5: Improve Maternal Health Indicator 16. Maternal mortality ratio Indicator 17. Proportion of births attended by skilled health personnel |  |  |  |  |  |  |  |
| JP Outcome 1: The inclusion of ethnic minorities in cultural, socio-economic and political life strengthened through improved public policies and services. (All of the outputs of Outcome 1 address all the MDGs targeted in this Joint Programme.) |  |  |  |  |  |  |  |
| 1. Governance processes made more inclusive of ethnic minorities and sensitive to culturally based development strategies. This component specifically targets MDG 0. Indicators are the number of successful trainings developed and provided. | 200 local government officials, local People’s Congress or CPPCC officials, community leaders and civil society representatives trained | Outcome reports Training material | Questionnaires, collection of documents, training workshops | UNDP, SEAC | 0 |  | 865 local government officials, local People’s Congress or CPPCC officials, community leaders, civil society and local community representatives trained |
|  | UNESCO Cultural Diversity Programming Lens Toolkit translated, adapted to the local context, tested and disseminated to minimum of 200 participants at the governance capacity-building workshops | Publication of the diversity lens toolkit in Chinese; Consultation meetings and training workshops evaluation reports; list of participants and meeting/training materials | Field visit, report and data collection | UNESCO, SEAC | Generic UNESCO Cultural Diversity Programming Lens Toolkit available in English |  | Diversity Lens Toolkit translated and disseminated to 168 workshop participants; Toolkit further adapted and tested based on local feedback Results originally not planned or intended: - Cultural Impact Assessment framework drafted and ready to be proposed to the session of Chinese Political People’s Conference in March 2012 by SEAC |
|  | At least 2 platforms for exchange on development strategies established | Recorded documents | Regular project progress report | UNDP, SEAC | 0 |  | Consultation workshop held in Congjiang to discuss issues of local community tourism development and strategies of long-term exchange mechanism |
| 2. Strengthened policy and institutional capacity in developing and implementing culturally sensitive and quality basic education for ethnic minority children. This component addresses MDG 2 and 3. The cited indicators specify how these goals will be achieved. | At least 60% of ethnic minority children in each of pilot schools fully informed about essential message on child-friendly and culture-sensitive schools | Baseline, field monitoring and interviews, end-line survey | Questionnaires, classroom observation | UNICEF and Ministry of Education | 0 |  | 100% of ethnic minority children in pilot schools were familiarized with child friendly and culture-sensitive schools through supply provision, including sports kits and library kits (in Mandarin & Tibetan) |
|  | At least 4 sets of local curricula developed for ethnic minority children living in pilot areas | Documents | Collection of documents | UNICEF and Ministry of Education | 0 |  | Local curricula outline for ethnic minority children living in pilot areas developed & 3 sets of local curricula finalized |
|  | At least 60% of ethnic minority teachers and school principals from pilot schools oriented towards child friendly and culture-sensitive teaching and management | Baseline, field monitoring and end-line survey | Questionnaires; Monitoring tools | UNICEF and Ministry of Education | 0 |  | 100% of ethnic minority teachers from pilot schools oriented on child friendly and culture-sensitive teaching and learning & 100% of teachers and principals trained on culture-sensitive management. |
|  | At least 2 pilot counties developed scaling up plan by the end of project cycle | Documents | Collection of documents | UNICEF and Ministry of Education | 0 |  | All 3 pilot counties developed and began implementing scaling up plan |
|  | 90% of available policies reviewed and analyzed and at least 12 case studies conducted involving both schools and communities | Documents, onsite verification | Desk review, field work | UNESCO MoE (NatCom) | 0 |  | 90% of available policies reviewed and analyzed and 12 cases studies conducted |
|  | At least 20 policy makers as well as 45 local practitioners enabled to use UNESCO’s policy recommendations and have participated in capacity building activities on framing and implementing culturally sensitive education policies for ethnic minority children | Documents | Desk review, checklist | UNESCO MoE (NatCom) | 0 |  | 20 local education officials and administrators trained on formulating and implementing culturally sensitive education policies for ethnic minority children |
| 3. Facilitate local adaptation of national MCH policy to assure improved participation in quality of, access to and knowledge and uptake of an essential package of evidence-based MCH and FP services and associated practices in ethnic minority areas, acknowledging culture and traditional beliefs as key influences on service strategies and uptake prioritized by local administrators, and incorporating improvements in human and financial resources, health systems and evaluation systems that specifically focus on the ethnicity of the providers and beneficiaries. This component addresses MDG 4 & 5. The detailed indicators listed show how this will be measured. | At least 60% of pregnant women in project counties who receive antenatal care at least 4 times (or alternatively 30% increase compared to baseline) | Baseline and end line surveys | Questionnaire | UNICEF UNFPA | Congjiang 39.85% Leishan 43.55% Luxi 71.29% Longchuan 47.06% Gyamda 5.88% Hualong 7.46% Average: 47.9% |  | Average: 77.7% |
|  | At least hospital delivery rate of 80% in project counties (or alternatively2 30% increase compared to baseline) | Baseline and end line surveys | Questionnaire | UNICEF UNFPA | Congjiang 53.04% Leishan 37.34% Luxi 76.12% Longchuan 79.87% Gyamda 28.2% Hualong 57.85% Average: 60% |  | Average: 92.7% |
|  | At least 30% of women undertaking exclusive breast feeding of their baby for 6 months (or alternatively2 50% increase compared to baseline) | Baseline and end line surveys | Questionnaire | UNICEF UNFPA | Congjiang 15.2% Leishan 30.8% Luxi 18.2% Longchuan 4.3% Gyamda 0% Hualong 18.2% Average: 17.5% |  | Average: 10.9% |
|  | At least 70% of MCH information staff trained on MCH information management system | Training materials, reports, Adapted guidelines | Training workshops | WHO | 45% |  | 45% |
| 4. Inclusion issues of minorities are better addressed through culture-based economic empowerment and non-discrimination. By addressing unequal access to employment for ethnic minorities, this component tackles MDG 1 and 3. The success of this component will be indicated by the numbers of ethnic minorities and especially the female population among these communities who are engaged in new venues of employment which can reduce their poverty. | At least 2 counties are able to institutionalize availability of quality data on the situation of ethnic minorities in the labour market | Validated research reports | Regular reporting | ILO | 0 |  | Data on the situation of ethnic minorities institutionalised in 4 counties |
|  | 50 labour officials with increased awareness and understanding of international labour standards and national legislation | Training attendance | Regular reporting | ILO | 0 |  | 177 labour officials with increased awareness and understanding of international labour standards and national legislation |
|  | 100 policy-makers, labour officials, advisors, employers and persons involved in the settlement of labour disputes with an in-depth understanding of the concepts of discrimination and equal opportunity | Survey on attitudes and experiences | Regular reporting | ILO | 0 |  | 182 stakeholders attended anti-discrimination training |
|  | In at least 2 counties a sustainable mechanism developed and implemented which will facilitate information exchange and training on anti-discrimination | Functioning mechanism | Regular reporting | ILO | 0 |  | Sustainable mechanism established in 4 counties for information exchange and training. |
|  | 10 non-pilot sites are using the training materials | Field visits | Regular reporting | ILO | 0 |  | 21 non-pilot sites are using the training materials |
|  | Two policy recommendations produced for local policy makers to decrease cultural and linguistic barriers and increase employment opportunities for ethnic minorities | Research papers and policy recommendations and workshops | Consultative (advisory) meetings | UNESCO, CASS | 0 |  | Baseline survey reports in 2 pilot counties on cultural and linguistic barriers to employment produced; research findings and recommendations disseminated at the final workshop |
| JP Outcome 2: Ethnic minorities empowered in management of cultural resources and benefiting from cultural-based economic development (The Outputs in JP Outcome 2 primarily address MDG 0, 1 and 3.) |  |  |  |  |  |  |  |
| 1. Improved approaches and capacity of ethnic minorities in understanding and protecting cultural (tangible and intangible) capital and ethnic awareness of cultural diversity This component addresses MDG 0, 1 and 3. The strategy centers on community-based involvement and ownership whose success will lead to improved governance and human rights. The component also targets the inclusion of women. The resulting community museums will bring increased income to the communities. | Ethnic minority communities’ production of own cultural maps in 5 or more villages in Congjiang County | Cultural mapping archives and final publication | Field visit, report and data collection | UNESCO | 0 |  | Ethnic minority communities’ production of own cultural maps ongoing in 11 villages in Congjiang County |
|  | Production of new exhibit and museum catalogue in 2 or more villages in Congjiang County incorporating results of community-based mapping | Analytical report of museum baseline survey and evaluation reports of museum training workshops; museum catalogue | Field visit and desk review | UNESCO | 0 |  | A new exhibit installed in 1 village museum in Congjiang County |
|  | Master Plan on 1) agro-culture dynamic conservation and 2) alternative industries development developed for Congjiang County | Master plan document; Training/workshop attendance; Publicity/advocacy documents | Monitoring in months 14, 24-25, 33-34 | FAO | No relevant Master Plan has been developed 0 0 |  | Outline of Master plan has been developed |
|  | 100 local stakeholders trained on conservation and development |  |  |  |  |  | 80 local stakeholders trained on conservation and development |
|  | 6 publications published and at least 2 public information exchange meetings organized advocating agro-culture |  |  |  |  |  | 3 publications & 10 articles published; 10 public information meetings organized; 1 documentary & 1 photo exhibition on agriculture heritage produced/organized; 1 agriculture heritage conservation and development exhibition organized |
| 2. Capacity built and examples piloted on using participatory processes in managing minority community resources and sustainability leveraging tourism for local livelihoods This component also addresses MDG 0, 1 and 3. The process of developing responsible, community-based tourism models will yield improved governance, gender equality and increased community incomes. | 120 local govt officials, community leaders and civil society representatives trained | Baseline, MTR, end line survey Training material | Questionnaires, collection of documents, Training workshops | UNDP, SEAC | 0 |  | 1,562 local govt officials, community leaders and civil society representatives trained |
|  | UNESCO Community-Based Tourism Capacity Building Handbook translated and disseminated to minimum of 50 participants at tourism consultations meetings and training workshops as well as 50 community residents | Publication of the toolkit in Chinese, consultation meetings and training workshops evaluation reports, list of participants and meeting/training materials | Field visit, report and data collection | UNESCO, SEAC | Generic UNESCO Community-Based Tourism Capacity Building Handbook available in English |  | Handbook translated and disseminated to 168 training participants, incl. 73 community residents |
|  | Responsible and participatory cultural tourism models at village and cross-village trail piloted (1 trail) | Onsite verification, reports | Field visit, regular progress report | UNDP, UNESCO, SEAC, local tourism administration | 0 |  | Participatory community tourism planning in 7 villages completed; community-based tourism development initiatives implemented in 7 villages |
| 3. Culture Based Local Economic Development (LED) and livelihood creation through: (i) provision of entrepreneurship and business development services, and (ii) strengthening policy and institutional environment for ethnic minority arts and crafts sector This component addresses MDG 1 and 3. The indicators provided all address the number of jobs and businesses to be reached by the trainings in this component, and how this will improve economic opportunities. Women ethnic minorities will be targeted. | Number of jobs has increased by 20% in the enterprises supported by the programme, at least 50% of which are held by women | County labour bureau statistics on employment | Included in the annual report | ILO, MOHRSS | 0% |  | Number of jobs has increased by 52.3% in the enterprises supported by the programme while women’s employment has increased by 63% in these enterprises |
|  | Marketability, quality and design of 2 product categories have been improved | Onsite verification, reports, survey | Field visit, data collection local staff recruited | UNIDO, SEAC | 0 |  | Training in design for new products in embroidery, brocade, textiles, silverware sectors creating over 65 new product designs; market assessment and test conducted through participation in trade fairs |
|  | Minimum of 40 businesses/artisans have received Entrepreneurship and Business Development Services (BDS) training | Onsite verification, reports | Field visit, meeting and interviews with counterparts and entrepreneurs | UNIDO, SEAC | 0 |  | Over 60 artisans/small business owners trained on aspects of business development including marketing, quality and business management |
|  | Minimum of 100 local stakeholders and craft-workers of ethnic minorities are trained on product development with emphasis on the balance of authenticity, innovation and marketing | Evaluation report, list of participants and training materials of the AWARD of Excellence Training Workshops | Field visit, report and data collection | UNESCO, CACA | 0 |  | 100 local stakeholders and crafts-workers of ethnic minorities trained on product development with emphasis on the balance of authenticity, innovation and marketing |
|  | Minimum of 100 stakeholders’ understanding of the local situation of artisans and craft industry, with a culturally sensitive approach, is improved to raise awareness among stakeholders on the role of cultural traditions in economic development | Evaluation report, list of participants and training materials of the Participatory Craft Survey Training Workshops and analytical report of the Participatory Craft Survey | Field visit, report and data collection | UNESCO, CACA | 0 |  | 130 stakeholders’ understanding of the local situation of artisans and craft industry, with a culturally sensitive approach, is improved to raise awareness among stakeholders on the role of cultural traditions in economic development; report on participatory craft survey currently being finalized |
|  | At least 2 provincial artisan networks and supporting institutions have been established or existing ones strengthened | Baseline and end line survey, consultation | Questionnaire, interview, consultation meeting | UNDP, SEAC | 0 |  | 2 county-level crafts associations established and strengthened & 1 prefectural-level association currently being established |

In counties where the base value is already too close to or exceeding the target value.