## Slide 1: I. Project Summary
Project Title | Socio-Economic Empowerment of Disadvantage (SEED) Youth in Liberia
Participating UN agencies | UNDP (Coordinating Agency) & UNFPA.
Implementation period | March 2019 – August 2020 (18 months)
Expenditure to date | UNDP - USD 209,200.00 (33%) out of USD 630,000.39 First tranche UNFPA - USD 151,805.28 (43%) out of USD 350,000.27 First tranche Total First Tranche - 361,005.28 USD (36.8%%) out of USD 980,000.66 PROJECT TOTAL: 361,005.28 (USD) 25.7%% out of 1,400,000.96

## Slide 2: II. Progress to date
Key achievements against the planned outcomes and outputs
Outcomes / Outputs | Results reported at the last meeting | Planned activities reported at the last meeting | Results delivered since the last meeting | On track / Off track
Outcome 1/ Output: 1 Capacity of three drop-in centers strengthened to provide psycho-social, mental and SRH services to 670 Zogos/Zogesse in Montserrado County | Drop in centers have been refurbished and equipped and services have commenced (details are included on the next slide) Screening process to select 500 out of the 1400 long list of disadvantaged youth is on-going; names of 250 to be given to CAFOD on September 15, 2019 Services at three Drop-in Centers: Psychosocial and health service provision: Number referred for clinical services: Redemption ( 10 persons/day) Sonniwein : 15 – 17/day ( made referral for last three weeks Duport Road : 28 persons referred in total Number TB annex: 7 ( West Point) Major health issues: Respiratory infections including tuberculosis, STIs, Malaria and Typhoid | Following up with MOH and YWCA to obtain the initial 250 case load for vocational training; | List of 223 names submitted to CAFOD to facilitate second phase of training needs assessment Meeting held with MSF and Plan International to support the implementation of the health component of the project considering management challenges with MOH MSF has a Psychiatrist and Psychologist in Country and plan support Omi Noir to conduct refresher training for social and health workers. MSF agreed to support MOH to finalize standards for health service delivery to substance abuse users | 

## Slide 3: II. Progress to date
Key achievements against the planned outcomes and outputs
  Coordination challenges due to conflicting schedules and time constraints.
Outcomes / Outputs | Results reported at the last meeting | Planned activities reported at the last meeting | Results delivered since the last meeting | On track / Off track
Outcome 1/ Output: 2: 500 Zogos/Zogesse rehabilitated, reintegrated and peacefully co-exist with community members in Montserrado County | The Catholic Agency for Overseas Development (CAFOD) and UNDP have signed a Standard Responsible Party Agreement for US$ 608k Planning sessions, preparation of training materials, procurement process completed with key stakeholders in preparation for the Orientation Sessions with community leaders, The LNP/LDEA and the Disadvantaged Youth Leaders scheduled for September 17, 18 and 19 respectively Recruitment process for two Consultants to develop IEC materials and harmonized UN peace-building manual is ongoing | Transferring the 1st NEX advance of USD186,000 to CAFOD; Orientation session for leaders of communities, LDEA and LNP, disadvantaged youth (Zogos/Zogese) on 17 -19 September | CAFOD received 1st tranche of funding stipulated in RPA agreement towards activity implementation. 3 Day orientation and sensitization of 250 community leaders, at-risk youth leaders and LNP and DEA personnel was conducted successfully. Final inputs shared by colleagues in Communication and RC Office; procurement process will be launched week of Oct 14th | On track On Track Delayed

## Slide 4: Challenges
Internal bottles necks and bureaucracy related procurement
Complete 500 case load of beneficiaries have not been turned over to CAFOD, which are presenting planning and logistical challenges for IP.
Drop-in centers have run out of medical supplies to treat at-risk youth.
Institutional capacity of implementing partners ( i. limited motivation for health workers including salary delayed and etc)

## Slide 5: III. Planned Activities
Key planned activities for the next one month:
  Conduct conflict prevention, mediation and social cohesion training
  Business skills/literacy and VSLA training with at-risk youth to begin, led by CAFOD
  Recruitment of consultants.
  Printing and dissemination of health-related and of IEC/BCC materials
  Payment of incentive for 15 Social Workers and 6 mental health clinicians
  Procurement of stationary for drop-in centers
  Conduct monitoring and supportive supervision at 3 drop-in centers
  Local Procurement of drugs and medical supplies by Plan International
  Work with Omi Noir and MSF to conduct training for social workers and clinicians