## Slide 1: I. Project Summary
Project Title | Socio-Economic Empowerment of Disadvantage (SEED) Youth in Liberia
Participating UN agencies | UNDP (Coordinating Agency) & UNFPA.
Implementation period | December 2018 – May 2020 (18 months)
Expenditure to date | UNDP - USD 16,540.00 (2.6%) out of USD 630,000.39 First tranche UNFPA - USD 94,698 (27 %) out of USD 350,000.27 First tranche Total First Tranche - USD 111,238 (11.4%) out of USD 980,000.66 PROJECT TOTAL: 111,238 USD 8% out of 1,400,000.96

## Slide 2: II. Progress to date
Key achievements against the planned outcomes and outputs
Outcomes / Outputs | Results reported at the last meeting | Planned activities reported at the last meeting | Results delivered since the last meeting | On track / Off track
Outcome 1/ Output: 1 Capacity of three drop-in centers strengthened to provide psycho-social, mental and SRH services to 670 Zogos/Zogesse in Montserrado County | Refurbishment work on integrated drop-in centers complete; furnishing ongoing Service delivery including SRHR outreach and psychosocial counseling , has commences Total reached with FP services - 1,790 10 cartoons of condoms contained 100 boxes of 144 pieces of condoms were distributed. A total of 144,000 condoms were distributed. Each client received 20 pieces, totaling 7,200 persons. HIV Counseling and Testing Pretest counseled – 196 Tested - 182 ( 33 females and 149 males) Positive - 1 Communication strategy final draft shared for UNFPA input Health-related IEC/BCC materials Data-base established for disadvantaged youth to include identification numbers | Work with UN Clinic to enable the procurement of mental health drugs to address the current stock-out at the drop-in centers Continue Psychosocial support and SRH Outreach Final Screening of long listing of disadvantaged youth to select 500 for skills training | Drop in centers have been refurbished and equipped and services have commenced (details are included on the next slide) Screening process to select 500 out of the 1400 long list of disadvantaged youth is on-going; names of 250 to be given to CAFOD on September 15, 2019 Services at three Drop-in Centers: Psychosocial and health service provision: Number referred for clinical services: Redemption ( 10 persons/day) Sonniwein : 15 – 17/day ( made referral for last three weeks Duport Road : 28 persons referred in total Number TB annex: 7 ( West Point) Major health issues: Respiratory infections including tuberculosis, STIs, Malaria and Typhoid | Delayed Delayed

## Slide 3: II. Progress to date
Key achievements against the planned outcomes and outputs
  Coordination challenges due to conflicting schedules and time constraints.
Outcomes / Outputs | Results reported at the last meeting | Planned activities reported at the last meeting | Results delivered since the last meeting | On track / Off track
Outcome 1/ Output: 2: 500 Zogos/Zogesse rehabilitated, reintegrated and peacefully co-exist with community members in Montserrado County | Micro Assessment for CAFOD ongoing Orientation Session concept note drafted and planning meeting with Partners scheduled to develop agenda Drafted TOR for recruitment of consultant to develop peacebuilding training manual | Working with CAFOD on budget and MOU Conduct orientation session involving community and Zogo leaders and LNP/LDEA Do e-req to recruit consultant to develop Harmonize and simplify UN peace-building materials and develop various training manuals for Zogos/Zogesse community leaders and other stakeholders. (1.2.2) | The Catholic Agency for Overseas Development (CAFOD) and UNDP have signed a Standard Responsible Party Agreement for US$ 608k Planning sessions, preparation of training materials, procurement process completed with key stakeholders in preparation for the Orientation Sessions with community leaders, The LNP/LDEA and the Disadvantaged Youth Leaders scheduled for September 17, 18 and 19 respectively Recruitment process for two Consultants to develop IEC materials and harmonized UN peace-building manual is ongoing | On track

## Slide 4: Challenges
Internal bottles necks and bureaucracy related procurement
Institutional capacity of implementing partners ( i.e limited motivation for health workers including salary delayed and etc)

## Slide 5: III. Planned Activities
Key planned activities for the next one month:
  Follow up with MOH/YWCA to obtain the initial case load for vocational training
  Work with CAFOD to get the 1st NEX advance of 186k