## Slide 1: I. Project Summary
Project Title | Socio-Economic Empowerment of Disadvantage (SEED) Youth in Liberia
Participating UN agencies | UNDP (Lead) & UNFPA.
Implementation period | December 2018 – May 2020 (18 months)
Expenditure to date | UNDP - USD 7,058 (%) out of USD 630,000.39 in total budget UNFPA - USD XXXX (XX %) out of USD 350,000.27 in total budget. TOTAL - USD XXXX out of USD 1,400,000.96 in total budget

## Slide 2: II. Progress to date
Key achievements against the planned outcomes and outputs
  Coordination challenges due to conflicting schedules and time constraints.
Outcomes / Outputs | Results reported at the last meeting | Planned activities reported at the last meeting | Results delivered since the last meeting | On track / Off track
Outcome / Output: 1 | One – on – one dialogue sessions and stakeholders consultations to help to allay concerns, allowed experience-sharing and lessons learnt from previous projects on engaging at-risk youth Community mapping and selection of health facilities completed to integrate drop-in centers Procurement process initiated to refurbish identified drop-in centers; procure drugs and medical supplies Joint Consultation Workshop with CSOs, NGOS, government institutions and health clinicians | Finalize communication strategy Complete health service providers training Community mapping and selection of health facilities completed to integrate drop-in centers Procurement process initiated to refurbish identified drop-in centers; procure drugs and medical supplies Tendering process ongoing for consultancy to develop communication strategy for the project | Micro Assessment for CAFOD ongoing Orientation Session concept note drafted and planning meeting with Partners scheduled to develop agenda TOR recruit consultant to develop peacebuilding training manual drafted | On track

## Slide 3: III. Planned Activities
Key planned activities for the next one month:
  Conduct orientation session involving community and Zogo leaders and LNP/LDEA
  Do e-req to recruit consultant to develop Harmonize and simplify UN peace-building materials and develop various training manuals for Zogos/Zogesse community leaders and other stakeholders. (1.2.2)
  Working with CAFOD on budget and MOU
  Financial Projection/Target = $150,00.00 (next 3 months).