China Culture and Development Annual Work Plan Color-coded

Green = done, yellow = ongoing, and red = not started

| JP output: 1.1 Governance processes made more inclusive of ethnic minorities and sensitive to culturally based development strategies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Annual targets |  | Activity |  |  | TIME FRAME 2009 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UN AGENCY |  |  | RESPONSIBLE PARTY |  |  | Planned Budget |  |  |  |  |  |
|  |  |  |  |  | Q1 |  |  |  | Q2 |  |  |  |  |  | Q3 | Q4 |  |  |  |  |  |  |  |  |  | Source of Funding |  |  | Budget description | Total amount |  |
| PMO set up, pilots selected, training needs identified, training of trainers and awareness raising activities conducted, results fed into revision of design, curricula and materials |  | 1.1.1. Preparation |  |  | × |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNESCO |  |  | SEAC |  |  | MGD-F |  |  | Personnel | 8,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 2,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 10,000 |  |
|  |  | 1.1.2. Training Workshops |  |  |  |  |  |  | × |  |  |  |  |  | × | × |  |  |  | UNESCO |  |  | SEAC |  |  | MGD-F |  |  | Contract | 9,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Con | 12,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 4,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 25,000 |  |
|  |  | 1.1.3. Toolkit in Chinese version ( & minority language as required) |  |  |  |  |  |  | × |  |  |  |  |  | × |  |  |  |  | UNESCO |  |  | SEAC |  |  | MGD-F |  |  | Contract | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 10,000 |  |
|  |  | 1.1.5. UNESCO Monitoring, evaluation and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  | UNESCO |  |  | SEAC |  |  | MGD-F |  |  | Contract | 5,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 2,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 7,000 |  |
|  |  | 1.1.6. Set up: PMO set up (AWP design) Needs assessment (AWP design) Pilot selection |  |  | × |  |  |  | × |  |  |  |  |  | × | × |  |  |  | UNDP |  |  | SEAC |  |  | MGD-F |  |  | Personnel I/L | 15,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 5,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies | 5,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 25,000 |  |
|  |  | 1.1.7. Training: Design Testing |  |  |  |  |  |  | × |  |  |  |  |  | × | × |  |  |  | UNDP |  |  | SEAC |  |  | MGD-F |  |  | Contract | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 8,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 28,000 |  |
| JP output: 1.2. Strengthened policy and institutional capacity in developing and implementing culturally sensitive and quality basic education for ethnic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline indicators on status of learning and teaching in the targeted ethnic minority areas identified |  |  | 1.2.1. Baseline studies on learning and teaching status for ethnic minority children and teachers - Field monitoring - Mid-term assessment - End-cycle assessment |  |  | × |  |  |  | × |  |  | × |  |  | × |  |  |  |  | UNICEF |  | MOE Provincial Education Commissions |  |  | MGD-F |  |  | Personnel I | 8,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 2,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 20,000 |  |
| Teachers trained in the targeted ethnic minority areas and school condition improved in safety and hygienic environment |  |  | 1.2.2. Development of teacher training materials in culturally appropriate languages |  |  | × |  |  |  | × |  |  | × |  |  | × |  |  |  |  | UNICEF |  | MOE Provincial Education Commissions |  |  | MGD-F |  |  | Contracts L | 40,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 60,000 |  |
| Outlines of guideline/training/teaching/learning materials drafted and consulted amongst UNICEF and implementing partners |  |  | 1.2.3. Workshops for developing outlines - contracts for technical support by consultants |  |  | × |  |  |  | × |  |  | × |  |  | × |  |  |  |  | UNICEF |  | MOE Provincial Education Commissions |  |  | MGD-F |  |  | Contracts | 25,000 |  |
|  |  |  | 1.2.4. Pre-testing in the field |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 25,000 |  |
| Supply provision to facilitate teacher training |  |  | 1.2.5. Supplies supported |  |  | × |  |  |  | × |  |  | × |  |  | × |  |  |  |  | UNICEF |  | MOE, Provincial Education Commissions |  |  | MGD-F |  |  | Supplies | 15,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 15,000 |  |
| Review of national and provincial policy on education for ethnic minorities |  |  | 1.2.6. Collection of national and provincial policy documents -Analysis from the minority perspective - Data processing |  |  | × |  |  |  | × |  |  | × |  |  | × |  |  |  |  | UNESCO |  | NatCom, MoE, College of Education of Central University for Nationalities (ECEUN) |  |  | MDG-F |  |  | Personnel I | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 8,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract | 22,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 40,000 |  |
| JP output: 1.3 Improved access to participation in quality of and knowledge and uptake of an essential package of evidence-based MCH and Family Planning (FP) services and associated practices in ethnic minority areas, acknowledging culture and traditional beliefs as key influences on service strategies and uptake, prioritized by local administrators, and incorporating improvements in human and financial resources, health systems management, and monitoring and evaluation systems that specifically focus on the ethnicity of the providers and beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline survey report drafted |  |  | 1.3.1. Conduct baseline survey |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNICEF |  |  | NCWCH |  | MDG-F |  | Contract |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 20,000 |
| Baseline survey report drafted |  |  | 1.3.2. Conduct baseline survey |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | China Population Development and Research Centre (CPDRC) & NFFPC |  | MDG-F |  | Contract |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 20,000 |
| Prepare and introduce culturally appropriate adaptations of national guidelines for training of MCH/FP service providers (UNFPA), and for counseling on MCH/FP choices National MCH guidelines adapted to local context |  |  | 1.3.3. Adaptation of national MCH guidelines |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNICEF |  |  | MCH Dept NCWCH PHB |  | MDG-F |  | Contract |  | 18,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supply |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 21,000 |
| National FP guidelines adapted to local context |  |  | 1.3.4. Adaptation of national FP guidelines |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | RH/FP institution under NPFPC |  | MDG-F |  | Contract |  | 18,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supply |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 21,000 |
| Training of provincial, county and township level health providers on MCH and health communication strategies, using community-based traditional leaders and health providers, and rollout an essential package of services (UNICEF) (includes iron, vitamin A, basic MCH equipment, vehicles) |  |  | 1.3.5. Training service providers. Provide vehicle Iron & VitA supplements. Provide computer. Provide medical equipment. |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNICEF |  |  | MCH Dept NCWCH PHB |  | MDG-F |  | Training |  | 55,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 12,600 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Personnel |  | 33,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Transportation |  | 99,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supply |  | 27,100 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 227,700 |
| Survey Report on Participation drafted |  |  | 1.3.6. Together with Baseline survey |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | CPDRC, and NCWCH |  | MDG-F |  | Contract |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 20,000 |
| Enhanced policy environment |  |  | 1.3.7. Workshops |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | NPFPC, NCWCH and Women Federation |  | MDG-F |  | Training |  | 56,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 56,000 |
| Improved household practices |  |  | 1.3.8. Community education |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNICEF |  |  | MCH, Dept NCWCH PHB |  | MDG-F |  | Training |  | 18,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supply |  | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract |  | 8,334 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 32,334 |
| Improved household practices |  |  | 1.3.9. IEC materials, media |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | NPFPC and MCH |  | MDG-F |  | Training |  | 56,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 56,000 |
| Technical assistance provided |  |  | 1.3.10. UNFPA CST visit |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | UNFPA |  |  | UFNPA CST in Bangkok |  | MDG-F |  | Personnel |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 5,000 |
| Draft integrating MCH service model in rural areas is available |  |  | 1.3.11.1. Situation analysis and literature review; |  |  |  |  |  |  |  | × |  |  | × |  |  |  | × |  |  |  | WHO |  |  | MOH |  | MGD-F |  | Personnel I |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Personnel N |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L |  | 28,000 |
|  |  |  | 1.3.11.2. Local essential medicines list(EML) for children |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 2,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 43,500 |
| MCH/FP essential package defined |  |  | 1.3.12.1. Literature review |  |  |  | × |  |  |  | × |  |  | × |  |  |  | × |  |  |  | WHO |  |  | MOH |  | MGD-F |  | Personnel L |  | 4,000 |
|  |  |  | 1.3.12.2. A review of local standards and guidelines and comparisons with essential package from National MCH Strategy and current implementation practices. Workshop to get consensus on local essential package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L |  | 36,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 44,000 |
| Standardized MCH data collection |  |  | 1.3.13.1. Adaptation of WHO guideline on data collection at grassroots level |  |  |  |  |  |  |  | × |  |  | × |  |  |  | × |  |  |  | WHO |  |  | MOH |  | MGD-F |  | Personnel I |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Personnel N |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L |  | 38,000 |
|  |  |  | 1.3.13.2. The establishment of causes of death at hospital and household levels. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  | 12,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 2,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 65,500 |
| Draft M&E framework developed |  |  | 1.3.14.1. Development of the action plan |  |  |  |  |  |  |  | × |  |  | × |  |  |  | × |  |  |  | WHO |  |  | MOH |  | MGD-F |  | Personnel I |  | 10,000 |
|  |  |  | 1.3.14.2. Conduct formative research to identify local barriers to care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L |  | 30,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 44,000 |
| JP output: 1. 4 Inclusion issues of minorities are better addressed through culture-based economic empowerment and non-discrimination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1. Research and surveys conducted, and policy and practical recommendations are used to formulate detailed capacity building strategy. |  |  |  |  |  | × |  |  | × |  |  |  | × |  |  | × |  |  |  | ILO |  |  | MOLSS |  |  | MGD-F |  |  | Contracts L | 20,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel | 5,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 35,000 |  |
| 1.4.2. Develop training materials for key stakeholders to better implement legislation |  |  |  |  |  |  |  |  | × |  |  |  | × |  |  | × |  |  |  | ILO |  |  | MOLSS |  |  | MGD-F |  |  | Contracts L | 10,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 10,000 |  |
| 1.4.3. Preparatory Phase, Literature and Policy Review Phase; selection of pilot sites, baseline study; training workshops, design/test overall strategies; consultative meetings; build project task force and partnership with local governments |  |  |  |  |  | × |  |  | × |  |  |  | × |  |  | x |  |  |  | UNESCO |  |  | CASS |  |  | MGD-F |  |  | Contracts L | 9,500 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Personnel | 1,000 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total | 10,500 |  |
| JP output: 2.1. Improved approaches and capacity of ethnic minorities in understanding and protecting cultural (tangible and intangible) capital and ethnic awareness of cultural diversity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness-raising of Cultural Mapping on a local level; implementation cultural mapping ;Museum enhancement |  |  |  | 2.1.1. Preparation phase |  |  |  | × |  |  |  | × |  |  | × |  |  |  | UNESCO |  |  |  | SACH |  |  | MDG-F |  |  | Personnel |  | 9,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract |  | 37,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 48,000 |
|  |  |  |  | 2.1.2. Cultural Mapping |  |  |  |  |  |  |  |  |  |  | × | × |  |  | UNESCO |  |  |  | SACH |  |  | MDG-F |  |  | Contracts |  | 16,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 16,000 |
|  |  |  |  | 2.1.3. Museum training and exhibition development |  |  |  |  |  |  |  |  |  |  | × | × |  |  | UNESCO |  |  |  | SACH |  |  | MDG-F |  |  | Contracts |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 8,000 |
| Awareness raising of traditional agro-culture in piloted minority areas |  |  |  | 2.1.5. Master plan development (field survey, literature preparation and outline) |  |  |  | × |  |  |  | × |  |  | × |  | × |  | FAO |  |  |  |  | MOA, IGSNRR |  | MGD-F |  |  | Personnel I |  | 18,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  | 9,750 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies |  | 5,650 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 20,100 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 55,000 |
| Dynamic conservation and adaptive management of these agro-culture systems |  |  |  | 2.1.6.1. Local workshop and training on traditional agro-culture MSP (multi-stakeholder process) in Congjiang county, Guizhou |  |  |  | × |  |  |  |  |  |  |  |  |  |  | FAO |  |  |  |  | MOA, IGSNRR |  | MGD-F |  |  | Personnel I |  | 13,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  | 6,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 24,000 |
|  |  |  |  | 2.1.6.2. Local workshop and training on traditional agro-culture MSP (multi-stakeholder process) in Luxi County, Yunnan |  |  |  |  |  |  |  | × |  |  |  |  |  |  | FAO |  |  |  |  | MOA, IGSNRR |  | MGD-F |  |  | Travel |  | 12,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 13,000 |
| Improvement of living standard in pilot minority area with traditional agricultural systems |  |  |  | 2.1.7. Publication and information exchange, etc. (two books and some articles) |  |  |  | × |  |  |  | × |  |  | × |  | × |  | FAO |  |  |  |  | MOA, IGSNRR |  | MGD-F |  |  | Personnel and Publication |  | 13,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 18,000 |
|  |  |  |  | 2.1.8. Workshop and training in Beijing |  |  |  | × |  |  |  |  |  |  |  |  |  |  | FAO |  |  |  |  | MOA, IGSNRR |  | MGD-F |  |  | Personnel I |  | 1,800 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  | 2,200 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies |  | 2,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  | 2,500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Miscell |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  | 10,000 |
| JP output: 2.2 Capacity built and examples piloted on using participatory processes in managing minority community resources and sustainably leveraging tourism for local livelihoods. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Needs identified, tourism handbook translated and training organized introducing community based cultural tourism. |  | 2.2.1. Preparatory phase |  |  |  |  |  | × |  |  |  |  |  |  |  |  |  |  | UNESCO |  |  |  |  | SEAC |  | MGD-F |  | Personnel |  |  | 9,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 11,000 |
|  |  | 2.2.2. Survey and needs assessment |  |  |  |  |  | × |  |  |  | × |  |  |  |  |  |  | UNESCO |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 8,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 8,000 |
|  |  | 2.2.3. Training Handbook translation |  |  |  |  |  |  |  |  |  | × |  |  | × |  |  |  | UNESCO |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 23,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training |  |  | 16,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 39,000 |
|  |  | 2.2.5. Monitoring, Evaluation and Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  | × |  |  | UNESCO |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 7,000 |
| PMO set up, needs assessment and market study conducted, results fed into planning of pilot models for local cultural tourism as well as training and awareness raising. processes, trainings conducted, consultants organized around pilot models, models revised based on feedbacks |  | 2.2.6. Set up: Needs assessment Market study PMO set up Pilot selection |  |  |  |  |  | × |  |  |  | × |  |  | × | × |  |  | UNDP |  |  |  |  | SEAC |  | MGD-F |  | Personnel I/L |  |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Supplies |  |  | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 30,000 |
|  |  | 2.2.7.Training Design Training |  |  |  |  |  | × |  |  |  | × |  |  | × | × |  |  | UNDP |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 8,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 1,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 9,000 |
|  |  | 2.2.8.Local Tourism Planning: Consultation Planning Drafting |  |  |  |  |  | × |  |  |  | × |  |  | × | × |  |  | UNDP |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 15,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 18,000 |
|  |  | 2.2.9. Consultation Design Implementation; Hospitality training Marketing |  |  |  |  |  | × |  |  |  | × |  |  | × | × |  |  | UNDP |  |  |  |  | SEAC |  | MGD-F |  | Contract |  |  | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 13,000 |
| JP output: 2.3 Culture Based Local Economic Development (LED) and livelihood creation through: - provision of entrepreneurship and business development services, and (ii) strengthening policy and institutional environment for ethnic minority arts and crafts sector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Potential entrepreneurs in cultural industries trained on SIYB |  | 2.3.1. Adaptation of training materials 2.3.2 Training of trainers 2.3.3 Training of entrepreneurs |  |  |  |  |  |  |  | × |  |  | × × × |  |  | × |  |  | ILO |  |  |  | MOLSS |  |  | MGD-F |  | Personnel L |  |  | 30,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 40,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 80,000 |
| Action plans developed for VCD on creative and traditional products |  | 2.3.4 Adaptation of VCD handbook 2.3.5 Training of VCD facilitators 2.3.6 Pilot VCD in the selected localities |  |  |  |  |  |  |  | × |  |  | × |  |  | × × |  |  | ILO |  |  |  | MOLSS |  |  | MGD-F |  | Personnel L |  |  | 15,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts L |  |  | 30,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 70,000 |
| PMO set up, trainings and awareness raising activities conducted, artisan networks and non-govt. craft associations identified and supported |  | 2.3.7. Set up Baseline analysis |  |  |  | × |  |  |  | × |  |  |  |  |  |  |  |  | UNDP |  |  |  | SEAC |  |  | MGD-F |  | Personnel I/L |  |  | 26,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 30,000 |
|  |  | 2.3.8. Design Training |  |  |  |  |  |  |  | × |  |  | × |  |  |  |  |  | UNDP |  |  |  | SEAC |  |  | MGD-F |  | Contract |  |  | 13,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 15,000 |
|  |  | 2.3.9. Design & Training (non-governmental minority craft associations and artisan networks ) |  |  |  | × |  |  |  | × |  |  |  |  |  |  |  |  | UNDP |  |  |  | SEAC |  |  | MGD-F |  | Contract |  |  | 13,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 15,000 |
| Pilot areas selected and potential cultural resources identified; sectoral assessment designed and undertaken; appropriate institutional structures developed |  | 2.3.10. Work team formed Preparatory phase |  |  |  | × |  |  |  |  |  |  |  |  |  |  |  |  | UNESCO |  |  |  | SEAC, CA&CA |  |  | MGD-F |  | Personnel |  |  | 9,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 18,000 |
|  |  | 2.3.11. Baseline study results |  |  |  |  |  |  |  | × |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MGD-F |  | Contracts |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 10,000 |
|  |  | 2.3.12. Market assessment results |  |  |  |  |  |  |  | × |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MGD-F |  | Contract |  |  | 12,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 12,000 |
|  |  | 2.3.13. Training workshops |  |  |  |  |  |  |  | × |  |  | × |  |  | × |  |  |  |  |  |  |  |  |  | MGD-F |  | Contract |  |  | 18,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training |  |  | 8,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 30,000 |
|  |  | 2.3.14. Training workshops (Participatory crafts survey Training) |  |  |  |  |  |  |  | × |  |  | × |  |  | × |  |  |  |  |  |  |  |  |  | MGD-F |  | Contract |  |  | 14,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Training |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 22,000 |
|  |  | 2.3.15. Survey (publication) (cost sharing with UNDP) |  |  |  |  |  |  |  |  |  |  | × |  |  | × |  |  |  |  |  |  |  |  |  | MGD-F |  | Contract |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 10,000 |
|  |  | 2.3.16. Reports (Monitoring & Evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |  | × |  |  |  |  |  |  |  |  |  | MGD-F |  | Contract |  |  | 9,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 14,000 |
|  |  | 2.3.17. UNIDO Preparatory phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIDO |  |  |  | SEAC |  |  | MGD-F |  | Personnel I/L |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 4,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 8,000 |
|  |  | 2.3.18. UNIDO identification of needs and consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIDO |  |  |  | SEAC |  |  | MGD-F |  | Personnel I/L |  |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 18,000 |
|  |  | 2.3.19. UNIDO Market and Product analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIDO |  |  |  | SEAC |  |  | MGD-F |  | Personnel I/L |  |  | 20,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contracts I/L |  |  | 40,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 14,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Equipment |  |  | 6,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 90,000 |
|  |  | 2.3.20 UNIDO Capacity building for business support services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIDO |  |  |  | SEAC |  |  | MDG_F |  | Personnel I/L |  |  | 10,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Train/Conf |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 5,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 20,000 |
|  |  | 2.3.21. M&E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNIDO |  |  |  | SEAC |  |  | MGD-F |  | Personnel I/L |  |  | 3,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Travel |  |  | 2,000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |  |  | 5,000 |
|  | Project preparation/formulation (Funds administered by UNFPA) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 19,580 |  |  |  |
|  | International Programme Coordinator (Funds to be administered by UNDP on behalf of UNRCO) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 65,343 |  |  |  |
|  | Total Planned Budget without management fee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,875,457 |  |  |  |
|  | Management Fee for MDG-F (7%) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 131,282 |  |  |  |
|  | Grand-Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,006,739 |  |  |  |

Includes $20,000 already advanced for programme formulation