KIRIBATI ONE UN FUND

Kiribati UNDAF Implementation Plan

2008 – 2012

UNDAF KIRIBATI IMPLEMENTATION PLAN 2008-2012

Equitable Economic Growth and Poverty Reduction (UNDAF Priority Area 1)

| Kiribati UNDAF Outcome 1.1: National and regional statistical information systems and databases are established, strengthened (to support information systems), upgraded and harmonised focusing strongly on demographic disaggregated data and poverty indicators. Kiribati Development Plan Policy Areas Addressed: Human Resources Development, Economic Growth and Poverty Reduction, Governance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| Policy Area 1 – Human Resources Development 1 Raising education standards and quality 1.4 Improving policy development, monitoring and evaluation, financial planning and use of data as a tool for effective planning Policy Area 2 – Economic Growth and Poverty Reduction 1 Increasing and expanding economic growth 1.13 Improve and update statistics and relevant information for planning and policy formulation Policy Area 5 – Governance 2 Updating and improving legal framework and enforcement 2.1 Review, update and develop regulations/legislation and strengthen enforcement mechanism at all levels 3 Improve and expand attention to the problems and/or concerns of women 3.1 Increase and promote the importance of the contribution of women to socio-economic development 3.2 Increase public awareness on gender-related issues 3.3 Increase support to services addressing gender-related issues 4 Improve and expand attention to the problems and/or issues of youth 4.1 Provision of quality services to youth 4.2 Support and encourage programs and operations addressing youth problems and issues 4.5 Encourage and promote partnerships with the community to address youth problems 6 Improve performance of Island Councils 6.1 Improve and enhance the knowledge and skills of island council staff and strengthen their institutions and systems 10.Promote and strengthen cultural values and traditions 10.1. Support and strengthen the role of unimwane and other traditional forms of governance in the community 10.2. Support and strengthen outer island community activities 11. Enhance support to disadvantaged and vulnerable groups (e.g. disabled, elderly, orphans, etc) 11.1. Review and determine type of support and assistance to such groups 11.2. Provide support for capacity building opportunities for such groups | 1a) Improved capacity of relevant officers & ministries to carry out, analyse & disseminate sex disaggregated and age-specific surveys on issues such as employment living standards, income distribution, etc | Data: Knowledge base on child youth and women - Strengthened capacity to develop, sustain MIS & reporting on children, youth and women - Youth labour market information - Career guidance counselling - Enhanced knowledge of formal and non-formal education and training systems on youth | - Number of UNICEF-supported qualitative, quantitative, and participatory community monitoring and evaluation reports produced by Social Sector Ministries and partners (and proportion that meet quality criteria) - Situation Analysis of Children and Women reports, CRC and CEDAW reports, reports against child-related MDGs and relevant Millennium Declaration Chapters, and WFFC Progress reports, prepared and submitted in a complete and timely manner - Proportion of national database that include disaggregated, gender-sensitive data on population and data, SRH & gender - Materials/reports developed and disseminated - One Regional Workshop and one national workshop on youth employment | $133k made up of: UNICEF $67k ILO $10k Gap - $56k | $698k made up of: UNICEF $419k ILO $20k Gap- $259k |
|  |  |  |  | Total funding required = $831,000 Total funding gap = $315,000 |  |
|  |  | Evidence Based: - Evidence-, rights- and MDG-based, pro-poor policies, plans, budgets and reports focused on children, women and adolescent girls, and youth | - Number of national and sectoral development plans aligned with MDGs and linked to national budgets - Number of policy and budget options developed for children made vulnerable by poverty, protection failures, disasters, and/or HIV/AIDS - Proportion of national and sectoral plans and policies that incorporate population, reproductive rights and address gender equality - Training programmes conducted and capacities enhanced on youth involvement in policy formulation especially youth employment - Promotion of the National Aid Management Database with relevant economic and social development indicators to monitor the achievement of the MDGs - Number of National MDG reports produced - Number of Government statisticians trained in reporting on the MDGs | $236k made up of: UNDP $104k UNICEF $47k UNFPA $15k ILO $20k Gap – $50k | $1140k made up of: UNDP $160k UNICEF $266K UNFPA $28k ILO $55k Gap – $631k |
|  |  |  |  | Total funding required = $1,376,000 Total funding gap = $681,000 |  |

| Kiribati UNDAF Outcome 1.2: Trade Mechanisms, private sector partnerships and employment generation are sustainable, pro poor and equitable Kiribati Development Plan Policy Areas Addressed: Economic Growth and Poverty Reduction |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| 1 Increasing and expanding economic growth 1.1 Develop and commercialize the fisheries, marine, and mineral resources 1.3 Stimulate and expand the private sector 1.4 Revitalize the replanting of staple food crops on all the islands 1.8. Improve, strengthen and diversify the copra industry 1.9 Expand and enhance production and export from Kiritimati (fish, prawns, solar salt, etc) 2. Increase employment rate and employment opportunities 2.2. Stimulate and expand the private sector 3 Increase and expand investment in productive sectors 3.1 Encourage private sector to invest in real or productive industries 4 Lowering the trade deficit 4.1 Diversify and broaden production and export base (e.g. solar salt ponds on Kiritimati, copra mill, pet fish, seaweed industry, etc) 4.2 Reduce imports through import-substitution and promotion of local produce 4.3 Improve quality of local products and promote them to tourists and overseas markets 4.4 Encourage private sector participation and foreign investment 4.5 Maximize benefits from regional and international trade agreements, e.g. PICTA, EPA, PACER, etc. | 1b) Improved mechanisms to facilitate trade and development | Trade Opportunities: - Enabling environment for enhanced trade supported by appropriate technologies for atoll agriculture developed through action research | - Number of appropriate technologies developed, disseminated and used by farmers - Increase investment flow into the agriculture sector - Increase in the number of registered businesses - Increase and diversification in number of products exported - Production of staple food crops increased - Rise in income levels and government revenue - Rise in ODA towards developing an enabling environment for enhanced trade and economic development | $843k made up of: UNDP $245k, FAO 490k, IFAD 108k Gap - $0k | 1192k made up of: UNDP $1,000k, FAO 100k, IFAD 92k Gap- $0k |
|  |  |  |  | Total funding required = $2,035,000 Total funding gap = $0 |  |
|  |  | Food Production: - Strengthening of traditional atoll food systems, production, preparation and preservation | - Available technologies documented, disseminated and used by farmers - Use of improved and sustainable agriculture systems increased - Increase in local produce - Greater variety in the number of locally produced products - Volume of trade of both local and export markets increased | $ 683k made up of: IFAD $108k, FAO $575k Gap – $0k | $ 742k made up of: IFAD $92k, FAO $650k Gap – $0k |
|  |  |  |  | Total funding required = $1,425,000 Total funding gap = $0 |  |
|  |  | Youth and Labour: - Integrated start-up pilot programmes incorporating cultural activities for young men and women to be developed in partnership with local providers | - Pilot programs to deliver and test new training and assistance packages - Two income generating initiatives focusing on young men and young women (based on craft, art/design, performing arts) successfully implemented in marginalized areas in Kiribati (to be discussed with local authority | $ 60k made up of: ILO $5k, UNESCO $5k Gap - $50k | $120k made up of: ILO $10k UNESCO $10k Gap - $100k |
|  |  |  |  | Total funding required = $180,000 Total funding gap = $150,000 |  |

UNDAF Implementation Detail – Kiribati UNDAF Outcome 1.1

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) | Remaining Indicators* |
| --- | --- | --- |
| Knowledge base on child youth and women | Joint Outputs - Strengthened capacity to develop, sustain MIS & reporting on children, youth and women - Youth labour market information - Career guidance counselling - Enhanced knowledge of formal and non-formal education and training systems on youth UNICEF Output - Line Ministry staff, Kiribati National Advisory Committee on Children (KNACC) members, partners, and rights holders more capable of researching, monitoring and evaluating child- and youth-related programmes through participatory processes and population-based survey (National/sub national) ILO Output - Gender sensitive career information and counselling materials developed and tested by key institutions and made publically accessible at affordable prices and through multi-media | - Career information and counselling materials publicly accessible and assisting youth |
| Statistics, Analysis and Reporting Mechanism | UNDP Outputs - Strengthened capacity among policy makers and CSOs to analyse trends and implications of key poverty, environment and gender issues and incorporate them in MDG based national policies, plans, budgets and reports UNICEF Outputs - Statistics staff within Social Sector Ministries, KNACC members, and staff from relevant units within Ministry of Finance and Economic Development, annually update, disseminate and use disaggregated data associated with CRC, CEDAW, WFFC goals, relevant Millennium Declaration Chapters, and child-related MDG targets and indicators (National) - Line Ministry staff, KNACC members, partners, and rights holders more capable of reporting progress on CRC and CEDAW implementation, child-related MDGs and relevant Millennium Declaration Chapters, and WFFC Goals, Targets and Indicators ILO Outputs - Desk review of existing qualitative and quantitative information on youth labour market and employment situation of young women and men; - Desk review of existing and formal and non-formal education and training systems and programmes for youth, and in particular for vulnerable youth UNFPA Outputs - Strengthened capacity of government to integrate population, gender equality and human rights, including the reproductive rights of women and adolescent girls, into national policies and development frameworks and to implement relevant interventions | UNDP Indicators - Number of national and sectoral development plans that are aligned with MDGs and linked to national budgets - Number of planners trained in MDG planning, budgeting, data collection and analyses - Number of staff trained in aid management and resource planning ILO Indicators - Report circulated and information widely disseminated and used as inputs in policy formulation and programme development and development of tools and guidelines for decent work for youth - One Regional Workshop and one national workshop on youth employment - Training programmes conducted and capacities enhanced - Career information and counselling materials publicly accessible and assisting youth - Pilot programs to deliver and test new training and assistance packages |

*Further indicators against agency outputs are described in the corresponding UN agency Country Programme Action Plan or equivalent

UNDAF Implementation Detail – Kiribati UNDAF Outcome 1.2

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) | Remaining Indicators* |
| --- | --- | --- |
| Trade Opportunities | Joint Output - Enabling environment for enhanced trade supported by appropriate technologies for atoll agriculture developed through action research UNDP Output - Enabling trade environment for enhanced trade in service/goods sectors FAO Output - Market /trade opportunities IFAD Output - Appropriate technologies for atoll agriculture developed through action research | IFAD - Number of appropriate technologies developed, disseminated and used by farmers FAO - Increase investment flow into the agriculture sector - Increase in the number of registered businesses - Increase and diversification in number of products exported - Production of staple food crops increased - Rise in income levels and government revenue |
| Food Production | Joint Output - Strengthening of traditional atoll food systems, production, preparation and preservation FAO Output - Food production IFAD Output - Appropriate atoll food production, preparation and preservation technologies from the Pacific region and elsewhere documented, disseminated and adopted | IFAD - Available technologies documented, disseminated and used by farmers FAO - Use of improved and sustainable agriculture systems increased - increase in local produce - Greater variety in the number of locally produced products - Volume of trade of both local and export markets increased |
| Policy Work on Trade | UNDP Outputs - Diagnostic studies - Costed Policy recommendations/options - Improved regulatory frameworks | UNDP - Number of laws relating to fair trading practices and private sector reviewed Baseline: Outdated fair trading and private sector laws; Target: Wide public consultations on revised fair trading and private sector laws |
| Food Processing | FAO Output - Food processing and value adding; and Coconut wood processing |  |
| Youth in Economic Activities | Joint Output - Integrated start-up pilot programmes incorporating cultural activities for young men and women to be developed in partnership with local providers ILO Output - Gender sensitive career information and counselling materials developed and tested by key institutions and made publicly accessible at affordable prices and through multi-media UNESCO Outputs - Country’s cultural diversity enhanced and promoted among young men and women - Greater appreciation of culture and traditions as viable source on livelihood - Greater participation of young men and women in sustainable, economic activities | - Pilot programs to deliver and test new training and assistance packages - Two income generating initiatives focusing on young men and young women (based on craft, art/design, performing arts) successfully implemented in marginalized areas in Kiribati (to be discussed with local authority) |

UNDAF Implementation Detail – Kiribati UNDAF Outcome 1.2 continued

| Youth Information | ILO Outputs - Desk review of existing qualitative and quantitative information on youth labour market and employment situation of young women and men; - Desk review of existing and formal and non-formal education and training systems and programmes for youth, and in particular for vulnerable youth | - Report circulated and information widely disseminated and used as inputs in policy formulation and programme development and development of tools and guidelines for decent work for youth |
| --- | --- | --- |
| Gender in Youth Employment | ILO Output - Gender sensitive career information and counselling materials developed and tested by key institutions and made publicly accessible at affordable prices and through multi-media | - Career information and counselling materials publicly accessible and assisting youth |
| Labour Policy for Youth | ILO Outputs - Multi-country and national workshops to facilitate the participation of tripartite constituents and youth networks in policy and programme development on Decent Work for the youth - Training of staff at the Ministry of Labour, employers and workers organizations and youth organizations to enhance capacities to influence policies and participate in policy and programme formulation and in the promotion of decent work for youth | - Training programmes conducted and capacities enhanced |

Good Governance and Human Rights (UNDAF Priority Area 2)

| Kiribati UNDAF Outcome 2.1: Pacific island countries demonstrate and uphold the Forum Principles of Good Leadership and Accountability. Kiribati UNDAF Outcome 2.2: Decentralisation of governance and participatory decision making is enhanced. Kiribati Development Plan Policy Areas Addressed: Governance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| 1. Improve auditing work 1.1 Strengthen capacity of KNAO 1.2 Encourage and enforce timely submission of public annual accounts 2. Updating and improving legal framework and enforcement 2.2 Promote awareness, education and understanding of legislation and regulations 2.3 Enhance partnership in the management and enforcement of legislation and regulations 8. Improve compliance to Public Account Committee (PAC) recommendations 8.1 Strengthen the PAC 8.2 Improve delivery and awareness of PAC output 8.3 Improve awareness of PAC role and impact of output 13. Strengthen public sector service delivery 13.1 Strengthen institutional capacity of the civil service and public enterprises 13.2 Encourage, support and promote public sector reform programs | 2a) Improved capacity of national parliaments to enable the efficient and effective performance of oversight, accountability, legislative and representative functions and roles | Parliamentary Support and Advocacy | - Number of Members of Parliament, disaggregated by sex, participating in the Induction Programme - Status of development of parliamentarian groups on Population and Development, Reproductive Health and Gender - Kiribati Parliamentary debates broadcast and web-streamed, and users able to search for archival audio or video items | $208k made up of: UNDP - $70k UNFPA - $10k UNESCO -$50k Gap - $78k | $662k made up of : UNDP - $110k UNFPA - $42k Gap - $510k |
|  |  |  |  | Total funding required = $870,000 Total funding gap = $588,000 |  |
| 6. Improve performance of Island Councils 6.1 Improve and enhance the knowledge and skills of island council staff and strengthen their institutions and systems 6.2 Continue support required by Island Councils 7. Improve development on outer islands 7.1 Provide and maintain alternative renewable energy on the outer islands 7.2 Develop appropriate water supply and sanitation systems 7.3 Develop telecommunication services on the outer islands 7.4 Ensure reliable and efficient transport means to the outer islands 7.5 Provide proper and adequate training on relevant and necessary skills 7.7 Strengthen and develop trade between outer islands and Tarawa 15. Improve coordination of government activities on Kiritimati 15.1 Review and strengthen MLPID for provision of greater planning, management and coordination role of Government services for Line and Phoenix groups | 2b) Broader and deeper participation of CSOs, communities and people in the development process at all levels, specifically in Island Council and Village Council initiatives 2e) Increased capacity of government ministries, island councils, village councils, churches, NGOs and other stakeholders to understand human rights obligations and to better plan, manage, implement and monitor local area development, including in relation to advancing the realization of human rights | Local Governance and Decentralization | - % of people actively engaged in councils and traditional systems - Number of participatory local level plans developed - Number of institutionalized planning & monitoring mechanisms in place between and across all levels of governance | $180k made up of: UNDP - $130k Gap - $50k | $1,440k made up of: UNDP - $240k Gap - $1,200k |
|  |  |  |  | Total funding required = $1,620,000 Total funding gap = $1,250,000 |  |

| Kiribati UNDAF Outcome 2.3: Pacific island countries are aware and protect human rights and make available mechanisms to claim them. Kiribati Development Plan Policy Areas Addressed: Governance |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area |  |  | Key Indicators |  | Budget (in US$) |  |  |
|  |  |  |  |  |  |  | Year 1 |  | Years 2-5 |
| 2. Updating and improving legal framework and enforcement 2.1Review, update and develop regulations/legislation and strengthen enforcement mechanisms at all levels 2.2Promote awareness, education and understanding of legislation and regulations 2.3 Enhance partnership in the management and enforcement of legislation and regulations 3. Improve and expand attention to the problems and/or concerns of women 3.1 Increase and promote the importance of the contribution of women to socio-economic development 3.2 Increase public awareness on gender-related issues 3.3 Increase support to services addressing gender-related issues 4. Improve and expand attention to the problems and/or issues of youth 4.1 Provision of quality services to youth; 4.2 Support and encourage programs and operations addressing youth problems & issues 4.4 Increase youth capacity and capability through vocational programs 4.5 Encourage and promote partnerships with the community to address youth problems 10. Promote and strengthen cultural values and traditions 10.1 Support and strengthen the role of unimwane and other traditional forms of governance in the community 10.2 Support and strengthen outer island community activities 11. Enhance support to disadvantaged and vulnerable groups (e.g. disabled, elderly, orphans) 11.1 Review and determine type of support and assistance to such groups 11.2 Provide support for capacity building opportunities for such groups 12. Improve status and conditions of public employees 12.1 Review the NCS, including its Procedures Manual, with a view to addressing the issues 12.2 Encourage, support and promote public sector reform 12.3 Ensure provision of basic needs of employees 12.4 Strengthen the roles of both PSO and PSC 13.Strenthen public sector service delivery 13.1 Strengthen institutional capacity of the civil service and public enterprises 13.2 Encourage, support and promote public sector reform programs | 2f) Improved capacity of States to ratify and implement core international human rights treaties, and to develop, establish and implement national and regional human rights mechanisms e.g. women and violence, child rights, HIV/aids, workers rights; improved capacity of individuals and communities to know about and claim their rights | National commitments to gender equality, women’s empowerment and children’s human rights implementation |  |  | - Degree of alignment between CEDAW legislative indicators, national laws and relevant human rights instruments - Increased capacity of National Women’s Machinery (MISA - Ministry of Internal and Social Affairs), National Council for Women (AMAK - Aia Maea Ainen Kiribati), civil society & key state actors in understanding gender equality and rights of the child and demonstrate effective advocacy & strategies to progress CEDAW & CRC implementation; advocate for gender responsive laws & policies at national, regional and global levels - Status of inclusion of Gender Based Violence (GBV) in pre and in service training of health care providers - Status of incorporation of reproductive rights into CEDAW and related reporting protocols |  | $210k made up of: UNIFEM - $40k UNICEF - $25k UNESCO - $15k UNFPA – $20k Gap - $110k |  | $2,308k made up of: UNIFEM - $120k UNICEF - $60k UNESCO - $22k UNFPA – $62k Gap - $2,044k |
|  |  |  |  |  |  |  | Total funding required = $2,518,000 Total funding gap = $2,154,000 Note: All UNESCO budgetary references for 2010 and beyond are indicative only and subject to endorsement by the UNESCO General Conference |  |  |
| 14. Improve and expand data or statistics for effective planning and policy formulation 14.1 Strengthen and enhance the capacity of statistical units in all Government agencies, an d in the island councils 14.2 Promote and strengthen use of statistics for management and planning purposes | 2c) Aid management systems developed and coordinated for effective up scaling for MDG achievement |  | All UN agencies are working together to improve the management and coordination of aid. The development of the UNDAF Kiribati Results Matrix and this UNDAF Implementation Plan are examples of this. |  |  |  |  |  |  |
|  | 2d) Increased capacity of stakeholders for civil registration |  | Civil Registration | - Proportion of children in three outer islands and on Tarawa (boys/ girls) under 5 registered |  | $50k made up of: UNICEF - $35k Gap - $15k |  | $200k made up: UNICEF - $50k Gap -$150k |  |
|  |  |  |  |  |  | Total funding required =$250,000 Total funding gap = $165,000k |  |  |  |

UNDAF Implementation Detail – Kiribati UNDAF Outcome 2.1

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) | Remaining Indicators* |
| --- | --- | --- |
| Parliamentary Support and Advocacy | UNDP Output - Improved capacity of national parliaments and government institutions and systems to enable the efficient and effective performance of oversight, accountability, legislative, representative functions and roles including improved capacity for equitable representation and participatory democracy through civic and human rights education | - Legislative Needs Analysis (LNA) updated - Number of oversight committee meetings held per year - Number of Sector Committee Reports presented in Parliament for Debates - Number of Select Committee Reports tabled in Parliament for Debates - Number of women with seats in national parliaments and oversight committees; number of political parties fielding female candidates for national and municipal election; number of female candidates in the national and municipal elections per year - Number of Public Submissions to Sector Committees - Number of Civil Society Organisations (CSOs) engaged in civic education in national programmes |
|  | UNFPA Outputs - Strengthened capacity of national policymakers, including parliamentarians, and of civil society to advocate for population and gender issues and for universal access to sexual and reproductive health information and services | - Number of parliamentary discussions on population, Reproductive Health (RH) and gender - Proportion of parliamentarians advocating population, sexual and reproductive health (SRH) and reproductive rights |

UNDAF Implementation Detail – Kiribati UNDAF Outcome 2.2

| Local Governance and Decentralization | UNDP Output - Increased capacity and participation of government ministries, island councils, village councils, churches, CSOs and community members in the development process at all levels | - Number of local councils leveraging ICT for planning and management |
| --- | --- | --- |
|  | UNESCO Outputs - Enhancement of freedom of expression; Kiribati media to collect, public/broadcast, and store community stories utilizing International Programme for the Development of Communication (IPDC) funding | - Capacity building training provided to Kiribati Broadcasting & Publications Authority (KBPA); - Extension of the KBPA signal to Line Islands Group; Capacity building training on advanced media/video/documentary production training given to young i-Kiribati media producers |

*Further indicators against agency outputs are described in the corresponding UN agency Country Programme Action Plan or equivalent

UNDAF Implementation Detail – Kiribati UNDAF Outcome 2.3

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) | Remaining Indicators* |
| --- | --- | --- |
| Gender and Human Rights | UNIFEM Outputs 1.1: Effective mechanisms for dialogue between government & Gender Equality advocates during NDS planning processes exist. 2.1Effective mechanisms for dialogue between government actors & Gender Equality advocates on how to develop constitutions/legal frameworks 4.1: Technical expertise on Gender Responsive Budgeting (GRB) is available to meet demands for supporting the incorporation of gender equality into budget processes. 5.1: National Women’s Machinery has increased their capacity to mainstream gender equality into National Develo0pment Strategies, laws, & policies. 5.2: Gender Equality experts, advocates & their organisations or networks have strengthened their capacity to advocate for gender responsive laws, policies & strategies at national, regional & global levels. 5.3: Governmental & NGO Gender Equality advocates participate effectively in mainstreaming gender equality into policy processes. 5.4: Women’s organisations, networks & movements have increased resources to support their long-term growth. 6.1: Women who are subject to exclusion &/or discrimination have enhanced capacities to participate in & influence all stages of planning, the development & implementation of relevant policies, programmes, budgets & processes. 6.2: Women who are subject to exclusion &/or discrimination & their organisations or networks have increased resources to support and sustain their advocacy work. 6.3: Women who are subject to exclusion &/or discrimination have increased access to relevant forums for voicing their priorities. 8.1: South-south exchanges enhance community level initiatives advancing women’s human rights & eliminating gender inequality. 8.2Effective models of community led initiatives advancing women’s human rights & eliminating gender inequality documented. | - Key national partners are partnering with gender equality advocates to engender the KDP. - Institutional arrangements & National Plan of Action for Gender Equality are put in place to ensure gender equality priorities in NDP. - Effective mechanisms for dialogue between government & actors & Gender Equality advocates on how to develop constitutions/legal frameworks/processes that promote & protect women’s human rights exist. - Finance Ministry, sectoral, ministries, provincial/local government that have in house expertise on GRB. - Number of civil society groups that can monitor budgets from a gender equality perspective. - National Women’s Machinery successfully mainstream gender quality into KDP. - % increase in advocacy activities of gender equality experts, advocates and their organisations/networks for gender responsive laws/policies including in the area of aid modalities. - Increase in media reports on common policy agendas that marginalized women’s groups are promoting. - Results of capacity assessments UNIFEM undertakes as follow up to training provided to women leaders. - Availability of documentation on successful strategies for addressing inter-linkages of VAW & HIV/AIDS. - Number of south-south learning exchanges documented. - Number of effective models implemented & documented. |
|  | UNICEF Outputs (1.1 and 1.2 National Level;1.3 Provincial Level) 1.1 Child Welfare and Protection Laws are aligned with the Convention on the Rights of the Child (CRC), and at least the Optional Protocol on the Sale of Children, Child Prostitution and Child Pornography and give authority to mandated agencies to enforce and apply them. 1.2 The judiciary , the police and social welfare officers / assistant social welfare officers apply principles of juvenile justice and have support programmes for young offenders, child victims and witnesses to protect their rights throughout the proceedings. 1.3 More “Unimanes”/ Island Councils in three outer islands and on South Tarawa & Betio practice principles of juvenile justice and child-friendly practices in line with national laws. | 1.1.2 Proportion of relevant stakeholders (male/female) who demonstrate ability to apply and implement Child Welfare and Protection Laws. 1.2.1 Increased proportion of cases appropriately diverted (police and court diversion) and children given alternative sentencing; 1.2.3 Proportion of child victims, offenders and witnesses who are provided proper protection and support by the relevant authorities at all stages of the criminal proceedings. 1.3.1 Proportion of “Unimanes”/Island Councils in three outer islands and on Tarawa who report understanding & applying child-friendly principles in resolving cases of minor offences by juveniles |
|  | UNFPA Outputs - Strengthened capacity of governments to integrate gender equality and human rights, including the reproductive rights of women and adolescent girls, into national policies and development frameworks and to implement relevant interventions - Increased advocacy and mechanisms for programme planners, managers and communities to apply the findings of studies on gender-based violence in selected Pacific Island countries and to develop and implement effective interventions to reduce gender-based violence. (Partners: SPC, CSOs, NGOs) | - Proportion of national plans and policies that address gender equality - Proportion of sectoral plans and policies that incorporate reproductive rights and address gender equality - Status of monitoring mechanisms for GBV at the national and provincial levels - Number of effective reduction interventions for GBV at national and provincial levels - Number of CSOs that actively promote inclusion of RH, Gender equality, women and girls’ empowerment and reproductive rights in HR protections systems |
|  | UNESCO Outputs 10.1.1 Increased Government officer skills in participatory policy development processes. 10.1.2 National Women’s Machinery’s (NWM) capacity to articulate women’s aspirations, identify women’s priorities and participate in policy development processes improved. 10.1.3 Improved understanding of poverty in the Pacific and its impact on women 10.1.4 Development of effective responses to Violence Against Women (VAW). | - Number of Government Ministries completed training - Number of NWMs trained - Number of country studies completed - Number of projects on VAW established and funded |

Equitable Social and Protection Services (UNDAF Priority Area 3)

| Kiribati UNDAF Outcome 3.1: Regional strategies, national policies and plans for equitable social and protection services are evidence-based and inclusive. Kiribati Development Plan Policy Areas Addressed: Human Resource Development |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| 1. Raising education standards and quality 1.1 Strengthening curriculum and assessment reform processes 1.2 Providing essential, quality teaching and learning materials, resources and equipment for schools 1.3 Strengthening school administration and leadership 1.4 Drafting and implementing policies in support of Education for All 1.5 Improving the implementation of the national teacher training system 2. Increasing retention and transition rates 2.1 Establish and promote technical and vocational education & training (TVET) 2.2 Raise public awareness of education policies and reform initiatives 2.3 Improve the maintenance and utilization of Education Management Information System (EMIS) for more effective and efficient education planning & monitoring | 3e) Increased availability of quality education services, especially for vulnerable groups | Early Childhood Care and Education (ECCE) - Child-centred, rights-based, evidence-based and inclusive pre-school policy - National relevant, outcome-based curriculum and assessment frameworks that are up to date, accessible to all children - Pre- and in-service teacher training and workplace support to teachers - Strategies for assessment and record keeping developed and implemented by teachers - Availability and use of quality teaching and learning guidelines and resources | - GER & NER ECCE - Percentage qualified ECCE personnel - Public expenditure on ECCE as % of total public expenditure on education | $160k made up: UNICEF $3k UNESCO $10k Gap - $147k | $500k made up: UNICEF-$50 UNESCO$60k Gap - $390k |
|  |  |  |  | Total funding required = $660,000 Total funding gap = $537,000 |  |
|  |  | Primary and Secondary - Teacher and School Head Education - Improved effectiveness of primary and secondary teachers for quality teaching and learning | - % of new entrants with ECCE - GER and NER primary and secondary - Percentage qualified primary, secondary teachers - Survival rate to grade 5 - Repetition rate by grade - Percent of grade 5+ who have mastered nationally defined basic learning competencies - National assessment results based on Literacy, numeracy and life-skills benchmarks - Public expenditure on ECCE as % of total public expenditure on education - Pupil-teacher ratio | $280k made up: UNICEF $10k UNESCO $100k Gap - $170k | $827k made up: UNICEF $90k UNESCO$200k Gap - $537k |
|  |  | Primary and Secondary – Management Information Systems (MIS) - Use of EMIS by all stakeholders (trained to use and to sustain) to monitor education sector development using EFA indicators and to inform and improve policy and planning practices |  | $110k made up UNICEF $10k UNESCO $20k Gap - $80k | $655k made up UNICEF $67k UNESCO $40k Gap - $548k |
|  |  | Primary and Secondary - School Curriculum and Assessment - Child-centred, rights-based, evidence-based and inclusive pre-school policy National relevant, outcome-based curriculum and assessment frameworks that are up to date, accessible to all children |  | $110k made up UNICEF $26k UNESCO $5k Gap - $79k | $560k made up UNICEF $84k UNESCO $40k Gap - $436k |
|  |  | Primary and Secondary - School Curriculum and Assessment - Child-centred, rights-based, evidence-based and inclusive pre-school policy - National relevant, outcome-based curriculum and assessment frameworks that are up to date, accessible to all children |  | $30k made up UNESCO $10k Gap - $20k | $80k made up UNESCO $20k Gap - $60k |
|  |  |  |  | $50k made up UNICEF $0k UNESCO $5k Gap - $45k | $200k made up UNICEF $0k UNESCO $30k Gap - $170k |
|  |  | Primary and Secondary - Education Personnel/ Administration Capacity Development |  |  |  |
|  |  | Primary and Secondary - Inclusive Education Policy - Child centred, evidence based inclusive education policy, publicized, developed and implemented in a participatory manner |  | $110k made up UNICEF $10k UNESCO $20k Gap - $80k | $655k made up UNICEF $67k UNESCO $40k Gap - $548k |
|  |  | Primary and Secondary – Total funding required and total gap |  | Total funding required = $3,667,000 Total funding gap = $2,773,000 |  |
|  |  | Technical Vocational Education and Training (TVET)/ Non Formal Education(NFE) – Policy, Curriculum and Instructor Training | - Transition rate secondary to TVET - NER TVET | $100k made up UNESCO $10k Gap - $90k | $400k made up UNESCO $30k Gap - $370k |
|  |  |  |  | Total funding required = $500,000 Total funding gap = $460,000 |  |

| Kiribati UNDAF Outcome 3.1: Regional strategies, national policies and plans for equitable social and protection services are evidence-based and inclusive. Kiribati UNDAF Outcome 3.2: National systems enhance accessibility, affordability and the well-managed delivery of equitable, gender-sensitive quality social and protection services. Kiribati Development Plan Policy Areas Addressed: Health |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators |  |  | Budget (in US$) |  |
|  |  |  |  |  |  | Year 1 | Years 2-5 |
| 1. Minimize child mortality rate 1.1. Expand and promote awareness programs on child health 1.2. Strengthen the implementation of IMCI programs 1.3. Develop and implement strategies to promote safe water and improve sanitation to improve child survival 2. Minimize maternal mortality rate 2.1. Improve delivery of services for maternal health through increased training of health workers 2.2. Provide quality adequate skilled care attendants during prenatal, childbirth and postnatal 2.3. Expand, promote and implement awareness on women’s health needs 3. Minimize and eliminate incidence of TB cases 3.1Improve coverage and delivery of TB control programmes 3.2 Increase national awareness and capacity in partnership with CSOs 3.3 Promote and increase coverage of preventive measures through public awareness 4. Minimize & control incidence of NCDs 4.1. Revise and implement the NCD prevalence plan 4.2. Improve the outreach of the NCD services 4.3. Improve the provision and delivery of public health services in terms of quality, accessibility, affordability, efficiency & effectiveness 4.4. Improve and expand coverage on awareness of the root causes and impact of NCD 4.5. Encourage the consumption of fresh nutritious local foods 5. Minimize and control incidence of HIV/AIDS 5.1 Improve and expand coverage on HIV/AIDS treatments and prevention 5.2. Develop training course & build capacity for caring HIV patients 5.3. Promote and implement practices that reduce the risk of HIV infection 5.4. Build capacity to effectively implement HIV education programs 5.5. Increase and improve availability of quality sexual and reproductive health services for youth 6. Minimize and control Sexually Transmitted Infections (STIs) 6.1. Improve diagnostic skill prevention and treatment 6.2. Increase and improve accessibility to services for STIs 6.3. Improve & promote monitoring & provision of services for STIs 6.4. Increase awareness of such diseases 7. Minimize and control hepatitis cases 7.1. Promote and increase awareness of the seriousness of hepatitis 7.2. Improve and expand coverage of preventative measures 7.3. Improve and maintain quality delivery of curative services 7.4. Encourage & promote alternative curative & preventive measures 8. Ensuring adequate stock of medical supplies 8.1. Improve the quality of health information as a tool for planning and decision making in the allocation of resources 8. 2. Improve/maintain outer island medical supply 8. 3. Improve and enhance communication between outer islands and the main hospital 9. Improving status of medical clinics on the outer islands 9.1. Improve and maintain provision of health services on the outer islands 9.2. Improve and maintain delivery of health services on the outer islands 9.3. Improve and maintain provision and delivery of health services in sub-urban areas 10. Improving delivery of services and performance of Nawerewere Central Hospital 10.1. Provide highly skilled, well supported, motivated and better performing health workforce 10.2. Strengthen and enhance capacity of administration and supporting staff 10.3. Provide more reliable health data and information 11. Monitor and control population growth 11.1. Promote family planning 11.2. Increase public awareness on the effects of a rising population 11.3. Address population congestion and overcrowding | 3d) TB & STI, HIV/AIDS mainstreamed into national strategic plans and linked to budgets 3f) Increased capacity to forecast, manage and distribute vaccines and essential drugs including CH/RH commodities (including improving contraceptive mix in outer islands) 3g) Strengthened institutional capacity of health service providers to deliver preventative & management services to at risk groups - children, women and people living with chronic illness 3h) HIV/AIDS planned, budgeted, implemented and monitored in collaboration with the regional programme on HIV/AIDS 3i) Strengthened health legislation drafted, enacted & enhanced implementation to comply with international health regulations 3k) Innovative models and approaches established and implemented for NCD control (drafting & enactment of legislation - smoking, alcohol, food import; community & school awareness education & fitness programmes) 3l) Increased availability of quality sexual and reproductive health services for young people 3n) Increased availability of services for promoting improved child survival | Child Survival - Immunization - Breastfeeding - Nutrition - Integrated Management of Childhood Illnesses (IMCI) - Continuity of Care - Treatment Guidelines - Water and Sanitation - Health seeking behaviour | - Proportion of one year old children immunized against measles - Proportion of infants less than 6 months of age exclusively breastfed. - Proportion of population with access to improved drinking water sources - Proportion of population with access to basic sanitation facilities - In hospital neonatal mortality rate - Increased % utilization of paediatric services |  |  | $485k made up of: UNICEF $200k WHO $15k Gap - $270k | $1,487k made up of: UNICEF $490k WHO $Nil Gap - $997k (inc. WHO $335k) |
|  |  |  |  |  |  | Total funding required = $1,972,000 Total funding gap = $1,267,000 |  |
|  |  | Maternal & Neonatal Health - Anti Natal Care (ANC) - Integrated Management of Pregnancy and childbirth - Emergency Obstetrics Care, - Skilled Birth Attendants training - National policies, strategies & programming on SRH | - Proportion of women attending at least 1 ANC and at least 4 ANCs - Proportion of births attended by skilled birth attendants - Proportion of SDPs offering basic emergency obstetric care |  |  | $286k made up of: UNICEF $79k UNFPA $20k Gap - $187k | $659k made up of: UNICEF $195k UNFPA $80k Gap - $384k |
|  |  |  |  |  |  | Total funding required = $945,000 Total funding gap = $571,000 |  |
|  |  | Non-Communicable Diseases - Primary prevention of NCDs - tobacco, diet and exercise, alcohol risk reduction - Secondary prevention in people with diabetes - Mental health - Disability Services | - Number of innovative models for NCD control established and implemented. - Number of interventions to improve care and diagnosis of people with chronic disease, disabilities and mental health problems |  |  | $241k made up of: WHO $76k Gap - $165k | $390k made up of: WHO $Nil Gap - $390k |
|  |  |  |  |  |  | Total funding required = $631,000 Total funding gap = $555,000 |  |
|  |  | HIV/AIDs (continued on the next page) - Leadership and HIV - HIV risk behaviour reduction (facilitate knowledge and skills acquisition for vulnerable groups of adolescents and youth) - Community participation in HIV prevention. (Support capacity development of CSOs and communities in HIV prevention efforts through participatory methods) - Prevention of Mother to Child Transmission (PMTCT) services & interventions. Capacity development of national ministries and provincial health administrations in planning and instituting integration of PMTCT services in reproductive health services, and in demand creation for these services. |  |  | - Condom use at last high risk sex - Proportion of ANC attendees and their partners) that receive integrated health promotion information at ANC clinics. | $109k made up: UNICEF $59k Gap - $50k | $960k made up: UNICEF $356k Gap - $604k |
|  |  |  |  |  |  | Total funding required = $1,069,000 Total funding gap = $654,000 |  |
|  |  | Sexual and Reproductive Health (Including Family Planning, STI/HIV Prevention & Treatment & Adolescent Sexual and Reproductive Health) - Family Planning promotion & Services - Youth friendly services and life skills based information - STIs prevention & treatment - HIV prevention |  | - Contraceptive Prevalence Rate - Proportion of people having adequate knowledge of more than three modern contraceptive methods - Proportion of SDPs offering at Youth Friendly SRH services - Prevalence of condom use at last high risk sex for males and females, 15-24 years of age. |  | $319k made up of: UNICEF - $73k UNFPA – $80k Gap - $166k | $1,500k made up of: UNICEF - $297k UNFPA – $38k Gap - $1,165k |
|  |  |  |  |  |  | Total funding required = $1,819,000 Total funding gap = $1,331,000 |  |
|  |  | Health System Strengthening - Health legislation - Human resources for health - Review, monitor and cost strategic plan - Health information - Supportive Supervision - Surveillance, response & disease elimination - Hospital Waste Management - Equipment replacement and maintenance planning - EPI and vaccine independence initiative - Pharmaceutical Management - Reproductive Health Commodity Security: forecasting, procurement, storage, distribution and logistics management |  | - Number legislation reviews - Number of staff enrolled in POLHN and other health professional courses - Percentage increase in achievement of quality standards - Number of interventions to strengthen surveillance and staff capacity reviewed - Number of surveillance, disease elimination reports - Numbers of health facilities /hospitals with access to medical waste incinerators or other means of proper disposal of medical waste. - Proportion of SDPs reporting stockouts for vaccines and essential drugs, contraceptives and RH commodities in the last twelve months |  | $387k made up of: WHO $312k Gap - $75k | $700k made up of: WHO Nil Gap - $700k |
|  |  |  |  |  |  | Total funding required = $1,087,000 Total funding gap = $775,000 |  |

| Kiribati UNDAF Outcome 3.2: National systems enhance accessibility, affordability and the well-managed delivery of equitable, gender-sensitive quality social and protection services. Kiribati Development Plan Policy Areas Addressed: Governance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| 2. Updating and improving legal framework and enforcement 2.1Review, update and develop regulations/legislation and strengthen enforcement mechanisms at all levels 2.2 Promote awareness, education and understanding of legislation and regulations 2.3 Enhance partnership in the management and enforcement of legislation and regulations (See also Strategy 4) | 3j) Families, communities and government system strengthened for effective protection of children and youths against all forms of abuse, neglect and exploitation in the home, community & institutions | Protection of Children Against Violence, Abuse, Neglect and Exploitation | - Proportion of cases (male/female) reported and addressed (at national and provincial level) in accordance with established operational procedures | $130k made up of: UNICEF - $20k - Gap - $110k | $535k made up of: UNICEF - $60k Gap - $475k |
|  |  |  |  | Total funding required = $665,000 Total funding gap = $585,000 |  |
| 4. Improve and expand attention to the problems and/or issues of youth 4.1 Provision of quality services to youth 4.2 Support and encourage programs and operations addressing youth problems and issues 4.3 Encourage and maintain youth programs as part of formal education 4.4 Increase youth capacity and capability through vocational programs 4.5 Encourage and promote partnership with the community 5. Minimize and control disorder and breaches of law 5.1 Involve churches, unimwane, and the community in fostering and maintaining law and order 5.2 Improve the capacity of KPS as well as update the laws necessary to allow effective and efficient policing 5.3 Strengthen and enhance capacities of the Office of the Attorney General and the Judiciary to help maintain law and order | 3m) Strengthened community policing, especially for children & young people | Community Policing | - Proportion of child victims, offenders and witnesses who are provided proper protection and support by the relevant authorities at all stages of the criminal proceedings | $20k made up of: UNICEF - $10k Gap - $10k | $100k made up of: UNICEF - $50k Gap - $20k |
|  |  |  |  | Total funding required =$120,000 Total funding gap = $30,000 |  |
| 11. Enhance support to disadvantaged and vulnerable groups (e.g. disabled, elderly, orphans, etc) 11.1 Review and determine type of support and assistance to such groups 11.2 provide support for capacity building opportunities for such groups | 3a) Increased institutional capacity to deliver high quality social and protection services for vulnerable groups aligned to a human-rights based approach | Social and Protection Services | - Proportion of cases of child abuse (male/female) reported and addressed (at national and provincial level) in accordance with established operational procedures | $250k made up of : UNICEF $30k Gap - $220k | $1,090k made up of: UNICEF $140k Gap - $950k |
|  |  |  |  | Total funding required =$1,340,000 Total funding gap =$1,170,000 |  |

UNDAF Implementation Detail – Kiribati UNDAF Outcomes 3.1 and 3.2

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) - Education | Remaining Indicators* |
| --- | --- | --- |
| Early Childhood Care and Education (ECCE) | Joint Outputs - The Ministry of Education (MoE) has a child centred, evidence based pre-school policy which is inclusive of linguistic, geographic and disability diversities. - Children have access to a sound, principled and human rights based ECE national curriculum and assessment framework which is regularly reviewed and which has relevant content including life skills and achievable and measurable outcomes that recognise the importance of bilingual competence and special needs. - ECE teachers participate in pre and in-service training and receive workplace support - ECE teachers have strategies for assessment and record keeping, student follow up and transfer, have adequate teaching and learning guidelines and sufficient good quality resources UNICEF Outputs - Early Childhood Education (ECE) personnel, in partnership with School Management Committees, parents and communities plan, implement, monitor and evaluate child centred formal and non formal education programmes that are inclusive of diversities in Kiribati (urban-outer island, special needs etc.). UNESCO Outputs - The Ministry of Education develops, implements and monitors Communication/Advocacy strategy to encourage participation - The Ministry of Education has ECE data needs identified, data collection and database established as part of KEMIS, with analysis conducted and reported. | - Participatory views of children and parents (particularly those most marginalised) systematically sought (through opinion polls, surveys etc) and used in pre-school policy development. - Proportion of ECE centres registered with MOE. - Proportion of ECE teachers who follow a syllabus based on national curriculum and who have records of lesson content, plans and learning outcomes achieved, for all enrolled children including those with special needs and appropriate to age and/or stage of cognitive development. - Proportion of ECE teachers integrating life skills, vocational skills and human rights education in classroom syllabus planning and delivery. - Proportion of ECE teachers using a bilingual approach to education. - Proportion of ECE teachers and other child educators who maintain portfolios for all students which contain student records of progress and achievement, samples of work, participation in extra-curricular activities as well as formative and summative assessment results. - Proportion of ECCE providers reporting adequate teaching and learning guidelines and sufficient quantity and quality of teaching and learning resources. - Proportion of ECE teachers and other child educators with core competencies in leadership and knowledge of Child centred schooling principles. - Immunization Indicators (examples): % of 1-year old children immunized against DPT3, Polio, Measles, Hepatitis, etc - Under-five mortality |

*Further indicators against agency outputs are described in the corresponding UN agency Country Programme Action Plan or equivalent

| Primary and Secondary Education: Teacher and School Head Education | Joint Outputs - Effectiveness of primary and secondary teachers improved through pre or in-service training and workplace support UNESCO Programme Outputs - Planning, management, evaluation and leadership skills of school principals / head teachers upgraded. - Capacities of teacher trainers in teacher training institutions strengthened in delivery of in-service training programme including a course on improvement of teacher effectiveness - Develop system of teacher performance appraisal and annual reporting - Enhanced capacities of MEYS staff with development of staff development policy for educational management and administration in school planning, management, evaluation and leadership mainstreamed in regular in-service / professional development programme UNICEF Programme Outputs - Primary and junior secondary teachers have strategies for assessment and record keeping, student follow up and transfer | - National training workshops on improvement of teacher effectiveness organized - National training workshops for school principals / head teachers organized - Teachers’ handbook on effectiveness made available and widely disseminated and used - Principals handbook on planning, management, evaluation and leadership developed, widely disseminated and used - 50% of teacher trainers trained and equipped with increased capacities to deliver classes on teacher effectiveness - Training programme on teacher effectiveness improvement and school planning, management, evaluation and leadership mainstreamed into regular pre-service and in-service programme in Kiribati Teachers College mainstreamed - The modules on teachers and principals on the above areas used as regular textbooks / resource materials for such mainstreamed training programme - Improved management and administration practices evident in policy documents and implementation in planning, management, evaluation and leadership, with two nationally funded staff training workshops held on an annual basis. - Proportion of primary and junior secondary teachers and other child educators who maintain portfolios for all students which contain student records of progress and achievement, samples of work, participation in extra-curricular activities as well as formative and summative assessment results. - Proportion of primary and junior secondary teachers and other child educators with core competencies in leadership and knowledge of Child centred schooling principles. - Transition rates primary-secondary - Repetition rates primary & secondary - Percentage of primary school teachers who are certified to teach according to national standards. |
| --- | --- | --- |
| Primary and Secondary Education: Education Management Information System (EMIS) | Joint Outputs - MoE senior management, Curriculum advisors, Education officers, school management committees with improved capacities, in partnership with communities and parents use KEMIS and other data capture mechanisms (e.g. STS, studies and evaluations) to measure achievement of EFA goals and associated indicators: Formal and non-formal education enrolment, transition and “push-out” rates for all students and schools; literacy and numeracy rates; teacher needs and quality of teaching; achievement of learning outcomes; parental, child and community attitudes to schooling; and how schools are managed. | - Proportion of registered child education providers (primary and junior secondary schools, ECE centres, non-formal education programmes) that track school and teacher performance based on CCS indicators. - Proportion of registered child education providers submitting Kiribati Education Management Information System (KEMIS) survey returns - Proportion of registered child education providers completing annual school self assessments. - Availability of thematic studies and participatory programme evaluations related to key issues in education for children of primary school age. - Improved policy decision making practices evident in policy documents with use of evidence (EFA indicators) - Participation of the Education Minister and the senior education ministry officials in Ministerial Ministers meetings and other high level fora fully informed about the status and outlook of national education system using evidence, and quality issues and solutions, and engaged in policy dialogue (using EFAInfo) |

| Primary and Secondary Education: School Curriculum and Assessment | Joint Outputs - Children have access to a sound, principled and human rights based primary and junior secondary school national curriculum which is regularly reviewed and which has relevant content including life skills and vocational education and achievable and measurable outcomes at each class/level that recognises the importance of bilingual competence and special needs. - Primary and junior secondary teachers and other child educators have strategies for assessment and record keeping, student follow up and transfer, educating children outside age cohort and out of school children, have adequate teaching and learning guidelines and sufficient good quality resources and receive pre- or in-service training and workplace support for leadership and child centred education. UNESCO Outputs - Progression and selection mechanisms defined in the curriculum, assessment and certification policies and procedures revised to provide improved pathways for vocational training and consistency with gender policies. - National assessments and certification aligned to revised curriculum - Literacy and numeracy monitoring system developed and implemented | - Proportion of primary and junior secondary teachers who follow a syllabus based on national curriculum and who have records of lesson content, plans and learning outcomes achieved, for all enrolled children including those with special needs and appropriate to age and/or stage of cognitive development. - Proportion of primary and junior secondary teachers integrating life skills, vocational skills and human rights education in classroom syllabus planning and delivery. - Proportion of primary teachers using a bilingual approach to education. - Proportion of primary and junior secondary teachers and other child educators who maintain portfolios for all students which contain student records of progress and achievement, samples of work, participation in extra-curricular activities as well as formative and summative assessment results. - Proportion of education providers for children reporting adequate teaching and learning guidelines and sufficient quantity and quality of teaching and learning resources. - Availability of literacy and numeracy monitoring system and evidence of implementation - Revised curriculum, assessment and certification policies with defined progression and selection mechanisms. |
| --- | --- | --- |
| Primary and Secondary Education: Administration/ Personnel Capacity Development | UNESCO Output - Enhanced capacities of MEYS staff with development of staff development policy for educational management and administration in school planning, management, evaluation and leadership mainstreamed in regular in-service / professional development programme that includes gender awareness and sensitization | - Improved management and administration practices evident in policy documents and implementation in planning, management, evaluation and leadership, with two nationally funded staff training workshops held on an annual basis. |
| Primary and Secondary Education: Inclusive Education | Joint Output - The Ministry of Education, Youth and Sport (MEYS) in partnership with communities and parents formulates, publicises and implements a child centred, evidence based inclusive education policy which recognises issues of linguistic and geographic diversities and special needs. | - Participatory views of children and parents (particularly those most marginalised) systematically sought (through opinion polls, surveys etc) and used in inclusive education policy development. |
| Technical Vocational Education and Training (TVET)/ Non Formal Education(NFE) | UNESCO Outputs - Increased access to and improved opportunities of non formal and TVET education and learning for youth with revised TVET policy including traditional skills and values for economic and social development - Improved capacities of NFE/TVET administrators and instructors - Increased availability of TVET courses and resources | - Increased proportion of youth with access to non formal and TVET education and learning opportunities as a result of policy revision and implementation - Number of trained/retrained TVET administrations and instructors - Youth Literacy Rate (15-24) - Adult Literacy Rate - Literacy Gender Parity Index - Proportion of youth taking part in TVET courses and using resources |

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) – Health | Remaining Indicators* |
| --- | --- | --- |
| Child Survival - Immunization - Breastfeeding - Nutrition - IMCI - Continuity of Care - Treatment Guidelines - Water and Sanitation | UNICEF Outputs - Immunization with potent vaccines more accessible and timely, especially in low performing districts - Parents and caregivers with children aged one year and under have knowledge of EPI and take children to be vaccinated at correct intervals - Infants less than six months are exclusively breast feed and infants older than 6 months receive appropriate complementary food. - Women and children have knowledge of a balanced diet with adequate micronutrient intake. - Children under 5 and pregnant women sleep under insecticide-treated bed nets in malarial areas every night. - Children with diarrhoea receive ORS and Zinc and continue feeding. - Children with suspected pneumonia are taken by parents to a health worker for treatment. - Children under five suffer fewer incidences of diarrhoea and other water related illnesses | - No. of country level “stock-outs” or additional vaccine orders per year - % of Health facilities with well maintained functioning refrigerators - No. of trained HWs competent in selected areas of EPI - % of mothers and caregivers with Knowledge of EPI – vaccines and age given or number of times to visit the clinic before the child is on year old - % hospitals with BFHI awards - % infants exclusively breastfed for the first six months of life - % of infants aged 6 to 24 months receiving complementary foods and breastfeeding - % of household consuming adequately iodized salts - % of children 6-59 months receiving two doses of vitamin A supplementation in a year - % of children under-five years of age reporting having slept under a bed net the previous night - % pregnant reporting having slept under a bed net the previous night - % of children with diarrhoea in the past two weeks who received ORS and Zinc and continued feeding - % of health facilities with no-stock outs of ORS and Zinc in a year - % of children with suspected pneumonia taken to a health worker/health facility for treatment - % of primary schools with access to improved water sources - % of primary schools with access to improved toilets - % of households with access to improved water sources - % of households with access to improved toilets |
|  | WHO Outputs - Staff trained in evidence based neonatal and paediatric hospital treatment guidelines - “At risk” neonates and 5yrs accessing intensive follow up care through continuity of care programme in South Tarawa - Water sources tested against quality standards Increase Health seeking behaviour among parents with babies and young children | - % decrease in in-hospital neonatal mortality - % of neonates and < 5yr olds in CCP admitted/readmitted to hospital - % drinking water sites tested that meet quality standards (UNICEF sites included in routine testing ) - % increase utilization of paediatric services |
| NCDs - Behavior change strategies for NCD prevention - Tobacco, diet and exercise, alcohol risk reduction Increased capacity to diagnose and care for people with chronic disease | WHO Output - People with disabilities have increased access to quality disability services - People with mental illness have increased access to quality primary and secondary mental health services - Increased access to effective primary prevention programmes to prevent NCDs - Increased access to secondary prevention programmes to prevent complications of diabetes | - % increase of people accessing disability services - % increase in people accessing appropriate mental health services - % of people involved in NCD risk behaviours ( STEPs survey) - % amputation for foot sepsis |

*Further indicators against agency outputs are described in the corresponding UN agency Country Programme Action Plan or equivalent

| Maternal Health - ANC, - Integrated Management of Pregnancy and childbirth - Emergency Obstetrics Care, - Skilled Birth Attendants training - National policies, strategies & programming on SRH | UNFPA Outputs - Increased national commitment and strengthened capacity to formulate/update, monitor and advocate for national policies, strategies, protocols and programmes on maternal health, EmOC - Enhanced capacity of service providers to undertake quality maternal health service delivery through on-going care throughout pregnancy, delivery and immediate post-partum, in compliance with National Standards and Guidelines and based on the findings from the FP/EmOC facility-based survey - Enhanced capacity of civil society and community organizations to conduct effective, targeted behaviour change communication interventions, with an emphasis on supporting maternal health UNICEF Outputs - Pregnant women are attended by skilled health personnel during ANC, and the immediate postpartum period | - Proportion of births attended by skilled birth attendants - Proportion of SDPs offering at least 3 critical SRH services - Proportion of SDPs offering basic emergency obstetric care - Proportion of SDPs within two hours of comprehensive emergency obstetric care facility - Caesarean Section as a percentage of live births - Status of inclusion of FP in postpartum and post-abortion care protocols |  |
| --- | --- | --- | --- |
| HIV/AIDs - Leadership and HIV - HIV risk behaviour reduction. - Community participation in HIV prevention. PMTCT services & interventions | UNICEF Outputs - Most at risk youth, women and their partner engage in HIV-risk reduction behaviours in selected areas by: (a) increased ( national and other partners) ability to design, implement, and evaluate comprehensive behaviour change program, and (b) establishing comprehensive HIV and STI behaviour change programmes and services are established and/or strengthened for vulnerable adolescents and youth - Communities engaged and own HIV prevention and care and support processes by: supporting CSOs and communities in developing, and delivery of community relevant and user-friendly preventive services. - ANC women and their partner in selected areas have access to and use quality services for PMTCT by: increased government ability to develop policy and plans, implement and evaluate program for integration of “PPCT plus” interventions in existing reproductive health services. - All mothers, partners and children living with HIV receive ARV therapy and care; by: (a) support development of in country system supporting early identification of exposed children; (b) support establishment of referral mechanism between SRH services and treatment centres; and (c) maintain technical support to community organizations providing care and support to children and parents living with HIV and their parents |  | Indicator 1.1.1: % of males and females aged 15-19 who had sex before the age of 15 in selected areas. Target: 80% of the most at risk young people aged 15-19 in selected areas Indicator 1.1.2: Prevalence of condom use at last high risk sex for males and females, 15-24 years of age in selected areas Target: 80% of the most at risk populations (disaggregated by sex and age) in selected areas Indicator 1.1.3: Number of Partners supported to develop and implement innovative approaches reaching under 14 years old who are identified to be most vulnerable Indicator .2.1: Communities in selected areas have participatory programmes to address HIV prevention, care and support to people vulnerable to HIV Target: 60% of communities in selected areas Indicator 1.2.2: Communities in selected provinces care for and support People Living with HIV/AIDS Target: 20% of communities in selected areas Indicator 3.1: Policy Guideline on integration of PMTCT services in reproductive health services developed/ adopted. Indicator 3.2: Minimum standards of services in health facility with PMTCT integration developed Indicator 3.3 Proportion of SDP with integrated PMTCT services Indicator 3.4 Proportion of ANC attendees accessing PMTCT services Target: 80% of ANC women in selected areas Indicator 3.5 Number of pregnant HIV positive women received complete package of PMTCT services Indicator 3.6 Proportion of male partners of ANC attendees supporting women to access PMTCT services Indicator 4. Proportion of HIV-exposed/positive children and HIV-positive women and their families in selected areas report they are benefiting from PMTCT interventions Target: 80% of HIV-exposed/positive children and HIV-positive women and their families in selected areas |
|  | UNDP Outputs - Enhanced engagement of leaders and decision makers at all levels to take immediate action on HIV involving people living with HIV/AIDS; and strengthened multi-sectoral planning. |  | - Number of people trained through Leadership for Development Programme disaggregated by sex - Number of legislation, policies and strategies reviewed and recommendations made to mainstream HIV/AIDS |
| Sexual and Reproductive health including Family Planning, STI/HIV prevention & treatment & Adolescent Sexual and Reproductive Health (ASRH) - Family Planning Promotion & Services - Youth friendly services and life skills based information - STIs prevention & treatment - HIV prevention | UNFPA Outputs - Increased national commitment and strengthened capacity to formulate/update, monitor and advocate for national policies, strategies, protocols and programmes on SRH including FP, ASRH, and STIs, including HIV - Enhanced capacity of institutions to undertake reproductive health evidence-based programme management, including planning, monitoring and evaluation; strengthening reproductive health information systems and relevant operations research - Strengthened institutional capacity to deliver comprehensive, integrated, high-quality sexual and reproductive health services including Family Planning counselling, information and services, in compliance with National Standards and Guidelines to the most at risk population, including young people - Increased availability of youth friendly services and information for sexual and reproductive health through support for models of service and information provision in community based clinics and schools. - Enhanced capacity of civil society and community organizations to conduct effective, targeted behaviour change communication interventions, with an emphasis on youth, promoting sexual and reproductive health, condom programming and responsible male involvement. - Increased country capacity to develop and implement STI/HIV prevention and control activities particularly for most at risk populations (Out of school youth & sex workers) | - Number of new or revised national policies on SRH, FP and STIs, including HIV. - Number of national strategies on SRH, FP, STIs, including HIV developed/revised - Proportion of SDPs offering at least three contraceptives - Proportion of SDPs offering at least 3 critical SRH services - Proportion of SDPs offering youth-friendly SRH services - Proportion of community leaders trained in advocacy and BCC promoting SRH - Proportion of people having adequate knowledge of more than three modern contraceptive methods - Proportion of community leaders trained in advocacy and BCC promoting SRH - Proportion of people having adequate knowledge of more than three modern contraceptive methods - Percentage of young men and women aged 15-24 who correctly identify ways of preventing the sexual transmission of HIV and reject misconceptions about HIV transmission |  |
|  | UNICEF Outputs 1.1. Most at risk youth, women and their partner engage in HIV-risk reduction behaviors in selected areas of Kiribati. 1.2. Traditional, religious, women leaders, local government representatives as well as teachers and health care workers, young people and People living with HIV in selected areas of Kiribati facilitate, plan, implement and monitor participatory programmes to address HIV prevention, care and support to people vulnerable to infection and those living with HIV 2.1. Antenatal clinic (ANC) attendees and their partners in selected areas of Kiribati have access to and use quality PMTCT services. 2.2 HIV positive children and HIV-positive women and their families in selected areas of Kiribati have access to and benefiting from PMTCT plus interventions. | 1.1.1 % of most at risk males and females aged 15-19 who have had sex before the age of 15 1.1.2 Prevalence of condom use at last high risk sex for males and females, 15-24 years of age. 1.2.1 % Communities in selected areas of Kiribati have participatory programmes to address HIV prevention, care and support to people vulnerable to infection and those who are living with HIV. - Communities in selected areas of Kiribati reported significant social changes related to HIV prevention, care and support. 2.1.4 Number of functional PMTCT sites in each of the selected areas of Kiribati. 2.1.1 Proportion of ANC attendees (and their partners) that receive integrated health promotion information at ANC clinics. 2.1. 2 Proportion of ANC attendees (and partners) at high risk of HIV referred to and use quality PMTCT Voluntary Confidential Counseling and Testing (VCCT) services. 2.2 1 Proportion of HIV-exposed/positive children and HIV-positive women and their families benefiting from PMTCT plus interventions. |  |

| Health system strengthening - Health policies, strategies and legislation - Human resources for health - Planning, Monitoring, costing and financial expenditure - Supportive Supervision - Health information - Surveillance & disease elimination - Health Services for people with physical disabilities - Mental health prevention and service delivery - Hospital Waste Management - Pharmaceutical Management - Reproductive Health Commodity Security: forecasting, procurement, storage, distribution and logistics management | WHO Outputs - Increased number of health legislation updated and meeting international requirements - Enhanced capacity of health staff in priority areas - Enhanced functioning of hospital based HI system - Enhanced health sector planning, monitoring and costing - Improved quality of health service delivery - Increased in disease surveillance - and elimination capacity - Development and implementation of hospital waste management plan - Development and implementation of major equipment replacement and maintenance plan | - Number of revised Bills to Cabinet - Number of health staff enrolled in POLHN and other courses - Number of reports on hospital data - Number of review, monitoring and costing reports - % increase in achievement of quality standards through supportive supervision - Number of surveillance /elimination strategy reports - Hospital waste management plan - Major equipment replacement and maintenance plan |
| --- | --- | --- |
|  | UNFPA Outputs - Increased national commitment and strengthened capacity to formulate/update national policies, strategies, protocols and programmes related to RHCS - Enhanced capacity of institutions, including Ministry of Health and relevant NGOs to ensure sustainable supply of contraceptives and other RH commodities including condoms with emphasis on strengthening advocacy for RHCS, improving logistics management systems and building capacity of relevant staff at sub-national levels | - Proportion of SDPs reporting stock-outs in contraceptives & RH commodities in the last 12 months - Number of NGOs undertaking condom programming - Proportion of the health budget allocated to contraceptives and RH commodities - Strategic Action Plan for RHCS for Kiribati formulated |

Sustainable Environmental Management (UNDAF Priority Area 4)

| Kiribati UNDAF Outcome 4.1: Environmental sustainability and sustainable energy are mainstreamed into regional and national policies, planning frameworks and programmes. Kiribati UNDAF Outcome 4.2: Pacific communities effectively manage and sustainably use their environment as well as their natural and cultural resources. Kiribati Development Plan Policy Areas Addressed: Environment |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Kiribati Development Plan Strategies | Kiribati UNDAF Output | UN Programmatic Theme/Area | Key Indicators | Budget (in US$) |  |
|  |  |  |  | Year 1 | Years 2-5 |
| 1. Protection and replenishment of natural resources 1.1 Encourage replanting of both staple food crops and other native plants 1.2 Ensure and maintain protection and conservation of agricultural and marine resources 2. Protection of island bio-diversity (i.e. plants, animals, and living systems) 2.1 Ensure and maintain protection and conservation of threatened island bio-diversity 2.2 Encourage and promote use of staple food crops, traditional herbal medicinal, cultural and other important native plants/ trees 2.3 Implementation and enforcement of the Environment Act and regulations 2.4 Prevent the introduction of dangerous foreign species 2.5 Establish and formalize the national Environment Advisory Committee (EAC) 2.8 Encourage and promote community participation 4. Improve and expand quality and supply of ground water 4.1 Enhance and maintain the water quality monitoring system 4.2 Increase public awareness on the sustainable use of water and the protection of water reserves 5. Monitor and control coastal erosion 5.1 Encourage and enforce protection of shoreline 5.2 Explore and develop other sources of mineral resources necessary for capital projects 5.3 Increase awareness and education on the impact of climate change 7. Combating and controlling impacts of development 7.1 Increase awareness on environmental issues 7.2 Promote and increase public awareness on the outcome and impact of projects | 4a) Strengthened national statistical information systems and databases focusing strongly on environment linkages to poverty 4b) Environment integrated into key national policy areas and plans 4c) Strengthened local institutional, legal and governance systems to improve marine and terrestrial environmental management, including invasive species 4d) Improved national and local supported adaptive capacities to address the adverse impacts of climate change | - MDG-based information systems and databases - National policies and plans - National and sub-national governance and adaptive capacities | - Percentage of national budgets dedicated to environment - Percentage of reserves managed by resource owners - Number of natural resource management plans utilized at national and sub-national levels - Number of protected areas (marine and terrestrial) | $398k made up of: UNDP - $35k UNESCO – $16k Gap - $347k | $1,450k made up of: UNDP - $56k UNESCO - $14k Gap - $1,380k |
|  |  |  |  | Total funding required = $1,848,000 Total funding gap = $1,727,000 |  |
|  |  | - National and sub-national governance capacities | - No. of established by-laws used by island councils for natural resource management & governance - Documented traditional practices used for natural resource governance - New approaches to groundwater resources monitoring and management adopted by national government | $244k made up of: UNDP - $10k UNESCO – $3k Current Partners - GEF Gap - $231k | $440k made up of: UNDP – none UNESCO - $12k Current Partners - GEF Gap - $428k |
|  |  |  |  | Total funding required = $684,000 Total funding gap = $659,000 |  |

UNDAF Implementation Detail – Kiribati UNDAF Outcomes 4.1 and 4.2

| UN Programmatic Theme/Area | UN Agency Specific Programme Outputs (CPAP/Biennium) | Remaining Indicators* |
| --- | --- | --- |
| Environmental Policy Development | UNDP Outputs - Strengthened national statistical information systems and databases focusing strongly on environment linkages to poverty - Environment integrated into key national policy areas and plans - Improved national and local supported adaptive capacities to address the adverse impacts of climate FAO Outputs - Strengthen agriculture, fisheries & forestry policies - Improve policy coordination UNESCO Outputs^ - Strengthened capacity to successfully design and implement local conservation and development initiatives for sustainable land management and information generation - Generation of new knowledge and establishment of new management practice on ground/freshwater resources - Establishment of a World Heritage adviser position with the Government of Kiribati to support the ongoing World Heritage site nomination, identification and expansion process ^ Partner: Ministry of Environment, Lands and Agricultural Development (MELAD); Public Utilities Board | - Number of government policies incorporating environmental responses and safeguards with proportionate national budget allocation for environment and sustainable development - Number of operational and formally recognized reserves, protection or conservation areas - Number of nationally owned and community based conservation or natural resource management projects (marine, aquatic, terrestrial) - Number of natural resource management plans formulated and utilized by management authorities or communities at national and sub-national levels. - Improvement in quality & quantity of primary products - Higher proportion of national budget to better management of environment and natural resources - Establishment of new Biosphere Reserve in North Tarawa and/or Kiritimati - Development of Biosphere Management Plan - Training for North Tarawa/Kiritimati communities living in the Biosphere reserve Area - Community-based conservation management projects to complement sustainable management of the Biosphere Reserve and provide for social and/or economic benefits - Capacity building in MELAD - Completion and publication of groundwater status and management report with reference to traditional practices - Development of related public policy responses - Development of related educational resources - Capacity building in MELAD & communities involved in natural resource management - Successful nomination of the Phoenix Islands World Heritage Area (world’s biggest marine protected area) - Development of firm plans for the extension of the World Heritage programme to include elements in the Line Islands Group in 2009-2011 - Decision taken on boundaries, management and institutional arrangements, and draft nomination document prepared for extended World Heritage Area including elements in both the Phoenix and Line Islands by 2011 - Strengthened overall management of natural resources and local development |
| Environmental Monitoring and Compliance | UNDP Outputs - Strengthened local institutional, legal and governance systems to improve marine and terrestrial environmental management, including invasive species FAO Outputs - Training in natural resources management | - Number of environmental legislation/strategies/reporting joint policing arrangements enacted and implemented - % of island councils managing their environment via established environmental by-laws and or incorporating (documented) traditional conservation knowledge and practices. - Published and documented information including lessons learnt relevant to environmental management, monitoring and compliance - Number of management plans formulated - Number of people in private and public sector trained |

*Further indicators against agency outputs are described in the corresponding UN agency Country Programme Action Plan or equivalent

All UNESCO budgetary references for 2010 and beyond are indicative only and subject to endorsement by the UNESCO General Conference

Partners include: Office of the Speaker, Ministry of Social and Internal Affairs with UN organizations, RRRT, CROP organizations, AUSAID, NZAID, CSOs, community members

Partners include: SPC, Forum Secretariat, UNDP sub-regional centre; United Nations Economic and Social Commission for Asia and the Pacific

Partners include: Ministry of Finance, Ministry of Internal and Social Affairs, Urban and Island Councils, Department of Planning with UN organizations, CROP organizations, CLGF, AUSAID, NZAID, ADB, JAPAN, CSOs, community members

Partners include: Commonwealth Parliamentary Association (CPA), UNDP; Kiribati Media Association

Includes magistrates, public defenders and prosecutors. Also includes lay-magistrates in outer islands.

Members of the judiciary, police officers, social workers, health care workers etc.

Including MISA, judiciary, police and other social service

Partners include: Ministries of: Health and Planning; Social Affairs; Home Affairs;  Education and Human Resources Development

All indicators to be disaggregated by gender, (dis)ability, sub-national levels to greatest extent possible

Budgets for Year 1 and 2-5 are all indicative; all UNESCO budgetary references for 2010 and beyond are subject to endorsement by the UNESCO General Conference

Selected areas identified based on an analysis of current prevalence of HIV and STI incidence are South Tarawa and 2 outer islands. Primary prevention targeting women and their partners will be supported by UNICEF. Primary prevention targeting young people will only be done through the AHD joint project (SPC/UNICEF/UNFPA joint project) and not by UNICEF.

Including MISA, judiciary, police and other social services

Note that this amount does not reflect support to education (UNESCO and UNICEF support); and support to HIV/AIDS prevention  (UNICEF supported)

EPI areas of competence: effective micro-planning and vaccine session planning; accurate vaccine forecasting and stock management; maintaining the cold chain and equipment maintenance; safe waste disposal; safe vaccine administration; use of hepatitis B outside the cold chain; and effective communication

Selected areas identified based on an analysis of current prevalence of HIV and STI incidence are South Tarawa and 2 outer islands. Primary prevention targeting women and their partners will be supported by UNICEF. Primary prevention targeting young people will only be done through the AHD joint project (SPC/UNICEF/UNFPA joint project) and not by UNICEF.

Selected areas: Based on an analysis of current prevalence of HIV and STI incidence and other parameters.

Selected areas identified based on an analysis of current prevalence of HIV and STI incidence are South Tarawa and 2 outer islands. Primary prevention targeting women and their partners will be supported by UNICEF. Primary prevention targeting young people will only be done through the AHD joint project (SPC/UNICEF/UNFPA joint project) and not by UNICEF.

Safe-motherhood Package which includes HIV and other maternal health related information

Quality PMTCT services include quality antenatal care (health education, rapid screening and treatment of Syphilis/Congenital Syphilis and Family planning), Universal HIV pre/post counseling and voluntary rapid testing, Partner involvement in counseling, Provision of anti-retroviral prophylaxis (ARV/ART), Counseling on safer infant feeding practice including safer breast-feeding practices, Safe delivery, Post-natal care for the infant (depending on country context) for PMTCT.

PMTCT plus interventions include encouraging partner involvement, linking PMTCT with community-based programs, and developing strong linkages to ongoing care and support of both mother and infant.

All UNESCO budgetary references for 2010 and beyond are indicative only and subject to endorsement by the UNESCO General Conference