- Liberia Peace building Fund

- QUARTERLY STATUS REPORT AS OF 31/03/10

| Recipient UN Organization: | UNDP |  | PBF Priority Area: |  | Critical interventions to promote peace and resolve conflict – Area 2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | Landmine Action |  |  |  |  |  |  |
| Project Number: | PBF/LBR/D-3 Chrono Ref: 006 |  |  |  |  |  |  |
| Project Title: | Tumutu Agricultural Training Programme |  |  |  |  |  |  |
| Total Approved Project Budget | $1,123,500 |  |  |  |  |  |  |
| Funds Committed: | $1,123,500 |  | Percentage of Approved: |  | 100% |  |  |
| Funds Disbursed: | $950,461.81 |  | Percentage of Approved: |  | 84% |  |  |
| SC Approval Date: | 25/09/08 |  |  |  |  |  |  |
| Expected Project Duration: | 18 Months | Forecast Final Date: |  | 03/10 |  | Delay (Months): | 0 |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Course II M&E complete | Completed, see attached report | 100% |
| Course III mid-term evaluations complete | Completed | 100% |
| Course III reintegration planning complete and final reintegration materials provided | Completed | 100% |
| Course III beneficiaries graduated | Completed | 100% |
| Course III beneficiaries relocated to chosen communities | Completed | 100% |

Qualitative achievements against expected results:

Please see separate report